## Slide 1
DECISION: SELECT OPTION C
Requested approval: $499k equipment investment, subject to the week-10 GO/HOLD gate (synthetic data)
$499k
Investment (one-time)
$162k
Annual saving per year
3.1 yrs
Simple payback (499 ÷ 162)
−$13k
3-yr net (3 × 162 − 499)
WHAT OPTION C DELIVERS
Highest saving ($162k/yr) and highest investment of the three. Reference uptime 99.9%, the only option above the 99.6% threshold. Option A has the shortest payback (2.7 yrs).
THREE-YEAR VIEW
Base case is −$13k after three years; downside −$110.2k, upside +$84.2k. Breakeven within three years needs $166.3k/yr (see Scenario).
CONDITION
Rollout proceeds only on GO at week 10: measured uptime ≥ 99.6%, all sites pass capacity validation, training and validation complete.
All figures are synthetic. $k = thousands of dollars.

## Slide 2
OPTIONS: THREE REFERENCE CONFIGURATIONS
Investment, annual saving and reference uptime as provided; reference options unchanged
Investment and annual saving by option ($k)
Chart: 
| Option A | Option B | Option C
Investment ($k) | 197 | 343 | 499
Annual saving ($k/yr) | 72 | 113 | 162
Side-by-side metrics
Metric | A | B | C
Investment ($k) | 197 | 343 | 499
Annual saving ($k/yr) | 72 | 113 | 162
Reference uptime (%) | 97.8 | 99.1 | 99.9
Simple payback (yrs) | 2.7 | 3.0 | 3.1
Three-year net ($k) | +19 | −4 | −13
Payback = investment ÷ annual saving; three-year net = 3 × saving − investment. Only C's reference uptime meets the 99.6% gate threshold; reference uptime is not proof of operational performance.

## Slide 3
PERFORMANCE: 110 UNITS BELOW SIX-MONTH TARGET
Monthly output M1–M6 versus a flat target of 1,100 units per month
Monthly output vs target (units)
Chart: 
| M1 | M2 | M3 | M4 | M5 | M6
Actual output | 860 | 790 | 1190 | 1350 | 1130 | 1170
Target | 1100 | 1100 | 1100 | 1100 | 1100 | 1100
6,490
Actual total (units)
6,600
Target total (units)
−110
Shortfall (units, −1.7%)
Variance vs target: M1 −240, M2 −310, M3 +90, M4 +250, M5 +30, M6 +70. Early deficit of 550 is offset by 440 surplus → net −110.

## Slide 4
SCENARIO: PAYBACK RANGES FROM 2.6 TO 3.9 YEARS
Option C, investment fixed at $499k; saving at 80% / 100% / 120% of $162k per year
Annual saving by scenario ($k/year)
Chart: 
| Downside (80%) | Base (100%) | Upside (120%)
Annual saving ($k/yr) | 129.6 | 162 | 194.4
Computed payback and three-year net
Scenario | Saving ($k/yr) | Payback (yrs) | 3-yr net ($k)
Downside | 129.6 | 499 ÷ 129.6 = 3.9 | 3 × 129.6 − 499 = −110.2
Base | 162.0 | 499 ÷ 162 = 3.1 | 3 × 162 − 499 = −13.0
Upside | 194.4 | 499 ÷ 194.4 = 2.6 | 3 × 194.4 − 499 = +84.2
BREAKEVEN WITHIN THREE YEARS
Requires saving ≥ 499 ÷ 3 = $166.3k/yr, about 2.7% above the base case. Only the upside scenario clears it.

## Slide 5
CAPACITY: NO SITE HAS DEMAND ABOVE CAPACITY
Daily demand vs daily capacity at North, East and West; West has the tightest margin
Daily demand vs capacity by site (per day)
Chart: 
| North | East | West
Daily demand | 223 | 277 | 319
Daily capacity | 240 | 310 | 330
Site check
Site | Demand / day | Capacity / day | Headroom | Utilization | Demand > capacity?
North | 223 | 240 | 17 | 92.9% | No
East | 277 | 310 | 33 | 89.4% | No
West | 319 | 330 | 11 | 96.7% | No
RESULT
Demand is within capacity at all three sites. West runs closest to its limit (96.7%, 11/day headroom). Site capacity validation remains a gate criterion.
Headroom = capacity − demand; utilization = demand ÷ capacity.

## Slide 6
ROADMAP: 14 WEEKS FROM DESIGN TO ROLLOUT
Technical and People lanes converge at the week-10 gate (drawn to scale; week 9 has no scheduled activity)
TECHNICAL
PEOPLE
Design
Weeks 1–2
Build
Weeks 3–5
Validate
Weeks 6–8
Train
Weeks 6–8
Gate
Wk 10
Rollout
Weeks 11–14
Validate and Train run in parallel in weeks 6–8, both starting after Build. Both must finish before the week-10 gate; rollout (weeks 11–14) starts only on GO.

## Slide 7
GATE: GO ONLY IF ALL THREE CRITERIA ARE MET
Week-10 decision rule; any unmet criterion results in HOLD
Criterion | Threshold for GO | Evidence at week 10
Uptime | At least 99.6% | Measured operational uptime, not the reference figure
Capacity | All sites pass (North, East, West) | Capacity validation result for each site
Readiness | Training and validation both finished | Completion of the weeks 6–8 workstreams
GO
All three criteria met → proceed to rollout, weeks 11–14
HOLD
Any criterion unmet → no rollout until resolved and re-tested
CAVEAT
Reference uptime is not proof of operational performance. Option C's reference uptime (99.9%) is 0.3 points above the 99.6% threshold, but GO still depends on measured operational uptime.

## Slide 8
RISK: SUPPLIER DELAY IS THE MORE LIKELY RISK
Likelihood (x) and impact (y), each scored 1–5, with planned mitigations
Impact (1–5) ↑
1
2
3
4
5
1
2
3
4
5
Likelihood (1–5) →
Supplier delay (L4, I3)
Training gap (L2, I4)
Risk | L | I | L × I | Mitigation
Supplier delay | 4 | 3 | 12 | Pre-order critical parts
Training gap | 2 | 4 | 8 | Supervised practice
READING THE MATRIX
Supplier delay is more likely (4 vs 2) and scores higher overall (12 vs 8). Training gap carries the higher impact (4 vs 3). Score = likelihood × impact, used as a ranking aid.
All data are synthetic.