## Slide 1
DECISION / Select option C
Commit to C as the preferred procurement path; release rollout only after the operational gate.
01 / 08
$528k
INITIAL INVESTMENT
$173k / year
ANNUAL SAVING • BASE CASE
3.1 years
SIMPLE PAYBACK • 528 ÷ 173
−$9k
THREE-YEAR NET • (3 × 173) − 528
Approval boundary: C is the selected procurement option. Operational GO still requires ≥99.6% uptime, capacity at every site, and completed training and validation.
SYNTHETIC DATA • Payback rounded to one decimal. Three-year net is undiscounted and assumes constant annual saving.

## Slide 2
OPTIONS / C is the highest-investment path
Reference options remain unchanged. C offers the highest annual saving and reference uptime.
02 / 08
Reference metric | Option A | Option B | Option C • selected
Investment ($k) | 214 | 366 | 528
Annual saving ($k/year) | 79 | 122 | 173
Uptime (%) | 97.8 | 99.1 | 99.9
B versus A
+$152k investment → +$43k/year saving
C versus B
+$162k investment → +$51k/year saving
C reference uptime: 99.9%, or 0.3 percentage points above the 99.6% operational GO threshold.
SYNTHETIC DATA • Reference uptime is not proof of operational performance.

## Slide 3
PERFORMANCE / Output reaches 89.1% of target
Three months exceed target, but the six-month cumulative shortfall remains 720 units.
03 / 08
MONTHLY OUTPUT • UNITS
Chart: 
| M1 | M2 | M3 | M4 | M5 | M6
Actual | 740 | 780 | 1120 | 1220 | 1110 | 910
Target | 1100 | 1100 | 1100 | 1100 | 1100 | 1100
Units | M1 | M2 | M3 | M4 | M5 | M6
Actual | 740 | 780 | 1,120 | 1,220 | 1,110 | 910
Target | 1,100 | 1,100 | 1,100 | 1,100 | 1,100 | 1,100
5,880 units
ACTUAL TOTAL
6,600 units
TARGET TOTAL • 6 × 1,100
720 units
SHORTFALL
6,600 − 5,880 = 720
SYNTHETIC DATA • Actual exceeds target in M3, M4 and M5. Attainment = 5,880 ÷ 6,600 = 89.1%, rounded.

## Slide 4
SCENARIO / C has a $9k base-case net deficit
A ±20% change in annual saving moves the three-year net by ±$103.8k.
04 / 08
ANNUAL SAVING • $k/YEAR
Chart: 
| Downside | Base | Upside
C annual saving | 138.4 | 173 | 207.6
C metric | Downside | Base | Upside
Saving vs. base | 80% | 100% | 120%
Saving ($k/year) | 138.4 | 173.0 | 207.6
Payback (years) | 3.82 | 3.05 | 2.54
3-year net ($k) | −112.8 | −9.0 | +94.8
Payback = 528 ÷ annual saving
Three-year net ($k) = 3 × annual saving − 528
Only the upside recovers the investment within three years; base-case payback is just over three years.
SYNTHETIC DATA • Investment $528k; constant saving within each scenario; undiscounted. Paybacks rounded to two decimals.

## Slide 5
CAPACITY / West needs 8 more units per day
Aggregate capacity is sufficient, but West demand exceeds its local capacity.
05 / 08
Site | Daily demand (units/day) | Capacity (units/day) | Headroom (units/day) | Demand check
North | 236 | 240 | +4 | Within capacity
East | 294 | 310 | +16 | Within capacity
West | 338 | 330 | −8 | ABOVE CAPACITY
NETWORK TOTAL
880 capacity − 868 demand = +12 units/day
GATE ACTION
Resolve West’s 8-unit/day gap and validate all sites.
Spare capacity elsewhere does not establish that West can meet demand; every site must pass validation.
SYNTHETIC DATA • Headroom = capacity − daily demand. Demand checks are arithmetic, not completed operational validation.

## Slide 6
ROADMAP / Two lanes feed the week 10 gate
Validate and Train run in parallel after Build; both must finish before the gate.
06 / 08
TECHNICAL
PEOPLE
Design
Weeks 1–2
Build
Weeks 3–5
Validate
Weeks 6–8
Train
Weeks 6–8
GATE
Week 10
Rollout
Weeks 11–14
DEPENDENCY LOGIC / Design → Build → Validate + Train → Gate → Rollout
SYNTHETIC DATA • Timing is a planned sequence. Rollout proceeds only after a GO decision.

## Slide 7
GATE / GO requires every condition
Week 10 is an evidence-based release decision. A missing or failed condition means HOLD.
07 / 08
Required condition | Evidence needed for GO
Operational uptime ≥99.6% | Measured operational performance meets threshold
All sites pass capacity validation | North, East and West each pass
Training finishes | Training completion confirmed
Validation finishes | Validation completion confirmed
GO
Only when all four
conditions are met
HOLD
Otherwise: resolve gaps
before rollout
Current inputs do not establish GO. C’s 99.9% reference uptime needs operational proof; West has an 8-unit/day capacity gap. Training and validation completion remain unconfirmed.
SYNTHETIC DATA • Reference uptime is not proof of operational performance. Completion evidence has not been supplied.

## Slide 8
RISK / Protect schedule and readiness
Supplier delay has higher likelihood; the training gap has higher impact.
08 / 08
1
2
3
4
5
1
2
3
4
5
IMPACT (1–5)
LIKELIHOOD (1–5)
Supplier delay (4, 3)
Training gap (2, 4)
SUPPLIER DELAY
Likelihood 4 • Impact 3
Mitigation: pre-order critical parts.
TRAINING GAP
Likelihood 2 • Impact 4
Mitigation: supervised practice.
SYNTHETIC DATA • Plot coordinates are (likelihood, impact), each on a 1–5 scale.