## Slide 1
EQUIPMENT PROCUREMENT · DECISION FOR APPROVAL
Select Option B
$366k investment returns $122k per year: simple payback 3.0 years, break-even at year 3.
WHY B
• Between A ($214k) and C ($528k) on cost; $162k less than C
• 99.1% reference uptime: +1.3 pts over A (97.8%)
• Conditional: week-9 gate needs ≥99.6% measured uptime, so B must prove it in operation
• West site demand is 8 units/day above capacity; fix before the gate
$366k
Investment
(one-time)
$122k
Annual saving
(per year)
3.0 yrs
Simple payback
366 ÷ 122
$0k
Three-year net
3 × 122 − 366
All data synthetic. Approval starts the 13-week roadmap; rollout proceeds only on a GO at the week-9 gate.

## Slide 2
Option B balances cost, payback and uptime
Three procurement paths · reference figures unchanged · $k unless stated
Metric | Option A | Option B · selected | Option C
Investment ($k) | 214 | 366 | 528
Annual saving ($k/yr) | 79 | 122 | 173
Reference uptime (%) | 97.8 | 99.1 | 99.9
Payback (yrs) = inv ÷ saving | 2.7 | 3.0 | 3.1
3-yr net ($k) = 3 × saving − inv | +23 | 0 | −9
Reference ≥ 99.6% gate? | No | No | Yes
READING THE TRADE-OFF
A: lowest cost and fastest payback, but weakest uptime (97.8%).
C: highest uptime (99.9%), but $528k and −$9k net after 3 years.
B: $162k below C, +1.3 pts uptime over A, and breaks even in year 3.
Reference uptime is not proof of operational performance. Only C's reference figure clears the 99.6% gate threshold; B must demonstrate ≥99.6% measured uptime during validation (see gate).

## Slide 3
Output ran 910 units (13.8%) below target over M1–M6
Monthly output vs 1,100-unit monthly target · current performance baseline
Units per month
Chart: 
| M1 | M2 | M3 | M4 | M5 | M6
Actual output | 740 | 780 | 1120 | 1030 | 1110 | 910
Target | 1100 | 1100 | 1100 | 1100 | 1100 | 1100
Month | Actual | Target | Gap
M1 | 740 | 1,100 | −360
M2 | 780 | 1,100 | −320
M3 | 1,120 | 1,100 | +20
M4 | 1,030 | 1,100 | −70
M5 | 1,110 | 1,100 | +10
M6 | 910 | 1,100 | −190
Total | 5,690 | 6,600 | −910
Shortfall: 910 units
6,600 − 5,690 = 910 (13.8% of target). Target met only in M3 and M5; M1–M2 account for 680 of the gap.

## Slide 4
Three-year result hinges on the full $122k saving
Option B saving at 80% / 100% / 120% of $122k per year · investment $366k
Annual saving, $k per year
Chart: 
| Downside (80%) | Base (100%) | Upside (120%)
Scenario saving | 97.6 | 122 | 146.4
Saving needed for 3-yr payback | 122 | 122 | 122
Scenario | Saving ($k/yr) | Payback (yrs) | 3-yr net ($k)
Downside 80% | 97.6 | 3.75 | −73.2
Base 100% | 122.0 | 3.00 | 0.0
Upside 120% | 146.4 | 2.50 | +73.2
Payback = 366 ÷ saving; 3-yr net = 3 × saving − 366
Downside: 366 ÷ 97.6 = 3.75 yrs; 292.8 − 366 = −73.2
Base: 366 ÷ 122 = 3.00 yrs; 366 − 366 = 0
Upside: 366 ÷ 146.4 = 2.50 yrs; 439.2 − 366 = +73.2
Each ±20% swing in saving moves the 3-yr net by ±$73.2k. Track realised saving monthly from rollout.

## Slide 5
West demand exceeds capacity by 8 units/day
Daily demand vs capacity by site · units per day · headroom = capacity − demand
Site | Daily demand (units/day) | Daily capacity (units/day) | Headroom (units/day) | Status
North | 236 | 240 | +4 | Within capacity
East | 294 | 310 | +16 | Within capacity
West | 338 | 330 | −8 | DEMAND ABOVE CAPACITY
Total | 868 | 880 | +12 | Net surplus masks West gap
North +4
1.7% headroom on 240 capacity
East +16
5.2% headroom on 310 capacity
West −8
Demand 2.4% above 330 capacity
Gate requires all sites to pass capacity validation: close West's 8 units/day gap (uplift, or evaluate shifting load to East's 16 spare) before week 9.

## Slide 6
13-week roadmap with a single go/no-go gate in week 9
Technical and People lanes · Validate and Train run in parallel after Build and both feed the gate
W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13
TECHNICAL
PEOPLE
Design
W1–2
Build
W3–5
Validate
W6–8
Train
W6–8
Gate
W9
Rollout
W10–13 · all sites
Critical path: Design (2 wks) → Build (3) → Validate + Train in parallel (3) → Gate (1) → Rollout (4) = 13 weeks
Validate and Train both start when Build ends (W5) and must both finish by W8; a slip in either holds the gate. Supplier delay is the main threat to Build (see risk).

## Slide 7
Week-9 gate: GO only if all three conditions hold
Every condition must pass; any single failure means HOLD
1 · Measured uptime ≥ 99.6%
Option B reference is 99.1%; reference uptime is not proof, so it must be measured in validation
2 · All sites pass capacity validation
Today West fails: demand 338 vs capacity 330 units/day (−8)
3 · Training and validation both finish
Both run weeks 6–8 after Build; the gate sits in week 9
ALL THREE
MET?
YES → GO
Proceed to rollout, weeks 10–13
NO → HOLD
Fix any unmet condition, re-test, re-gate
Reference uptime is not proof of operational performance: the 99.6% test uses measured uptime from validation, not the 99.1% reference figure.

## Slide 8
Supplier delay is the top risk: pre-order critical parts
↑ IMPACT (1–5)
5
4
3
2
1
1
2
3
4
5
LIKELIHOOD (1–5) →
Supplier
delay
Training
gap
Risk (L, I) | Score = L × I | Mitigation
Supplier delay (L4, I3) | 4 × 3 = 12 | Pre-order critical parts to protect Build (W3–5)
Training gap (L2, I4) | 2 × 4 = 8 | Supervised practice during Train (W6–8)
Priority | 12 > 8: act on supplier delay first | Training gap: lower likelihood, higher impact (4)