## Slide 1
EQUIPMENT PROCUREMENT · DECISION FOR APPROVAL
Select Option C
$528k investment returns $173k per year: simple payback 3.1 years; three-year net −$9k.
WHY C
• Highest annual saving: $173k, +$51k/yr vs B and +$94k/yr vs A
• 99.9% reference uptime: the only option above the 99.6% gate threshold (reference, not proof)
• Trade-off: largest outlay, $162k more than B; −$9k net at year 3
• West site demand is 8 units/day above capacity; fix before the week-10 gate
$528k
Investment
(one-time)
$173k
Annual saving
(per year)
3.1 yrs
Simple payback
528 ÷ 173 = 3.05
−$9k
Three-year net
3 × 173 − 528
All data synthetic. Approval starts the 14-week roadmap; rollout (weeks 11–14) proceeds only on a GO at the week-10 gate.

## Slide 2
Option C delivers the highest saving and uptime, at the highest cost
Three procurement paths · reference figures unchanged · $k unless stated
Metric | Option A | Option B | Option C · selected
Investment ($k) | 214 | 366 | 528
Annual saving ($k/yr) | 79 | 122 | 173
Reference uptime (%) | 97.8 | 99.1 | 99.9
Payback (yrs) = inv ÷ saving | 2.7 | 3.0 | 3.1
3-yr net ($k) = 3 × saving − inv | +23 | 0 | −9
Reference ≥ 99.6% gate? | No | No | Yes
READING THE TRADE-OFF
A: lowest cost and fastest payback (2.7 yrs), but weakest uptime (97.8%).
B: breaks even at year 3, but 99.1% uptime is below the 99.6% gate.
C: $173k/yr and 99.9% uptime; costs $162k more than B and nets −$9k at year 3.
Reference uptime is not proof of operational performance. C's 99.9% reference clears the 99.6% gate threshold on paper; it must still be demonstrated as measured uptime during validation.

## Slide 3
Output ran 720 units (10.9%) below target over M1–M6
Monthly output vs 1,100-unit monthly target · current performance baseline
Units per month
Chart: 
| M1 | M2 | M3 | M4 | M5 | M6
Actual output | 740 | 780 | 1120 | 1220 | 1110 | 910
Target | 1100 | 1100 | 1100 | 1100 | 1100 | 1100
Month | Actual | Target | Gap
M1 | 740 | 1,100 | −360
M2 | 780 | 1,100 | −320
M3 | 1,120 | 1,100 | +20
M4 | 1,220 | 1,100 | +120
M5 | 1,110 | 1,100 | +10
M6 | 910 | 1,100 | −190
Total | 5,880 | 6,600 | −720
Shortfall: 720 units
6,600 − 5,880 = 720 (10.9% of target). Target met in M3–M5; M1–M2 misses total 680 units.

## Slide 4
Three-year net turns positive only if saving beats the base case
Option C saving at 80% / 100% / 120% of $173k per year · investment $528k
Annual saving, $k per year
Chart: 
| Downside (80%) | Base (100%) | Upside (120%)
Scenario saving | 138.4 | 173 | 207.6
Saving for 3-yr break-even (528 ÷ 3) | 176 | 176 | 176
Scenario | Saving ($k/yr) | Payback (yrs) | 3-yr net ($k)
Downside 80% | 138.4 | 3.8 | −112.8
Base 100% | 173.0 | 3.1 | −9.0
Upside 120% | 207.6 | 2.5 | +94.8
Payback = 528 ÷ saving; 3-yr net = 3 × saving − 528
Downside: 528 ÷ 138.4 = 3.8 yrs; 415.2 − 528 = −112.8
Base: 528 ÷ 173 = 3.1 yrs; 519 − 528 = −9.0
Upside: 528 ÷ 207.6 = 2.5 yrs; 622.8 − 528 = +94.8
3-yr break-even needs ≥$176k/yr (528 ÷ 3), 1.7% above base. Each ±20% swing moves the 3-yr net by ±$103.8k.

## Slide 5
West demand exceeds capacity by 8 units/day
Daily demand vs capacity by site · units per day · headroom = capacity − demand
Site | Daily demand (units/day) | Daily capacity (units/day) | Headroom (units/day) | Status
North | 236 | 240 | +4 | Within capacity
East | 294 | 310 | +16 | Within capacity
West | 338 | 330 | −8 | DEMAND ABOVE CAPACITY
Total | 868 | 880 | +12 | Net surplus masks West gap
North +4
1.7% headroom on 240 capacity
East +16
5.2% headroom on 310 capacity
West −8
Demand 2.4% above 330 capacity
Gate requires all sites to pass capacity validation: close West's 8 units/day gap (uplift, or evaluate shifting load to East's 16 spare) before the week-10 gate.

## Slide 6
14-week roadmap with a single go/no-go gate in week 10
Technical and People lanes · Validate and Train run in parallel after Build and both feed the gate
W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14
TECHNICAL
PEOPLE
Design
W1–2
Build
W3–5
Validate
W6–8
Train
W6–8
Gate
W10
Rollout
W11–14 · all sites
Schedule: Design (2 wks) → Build (3) → Validate + Train in parallel (3) → W9 → Gate W10 (1) → Rollout (4) = 14 weeks
Validate and Train both start when Build ends (W5) and must both finish by W8; week 9 has no scheduled activity before the week-10 gate. A slip in either holds the gate. Supplier delay is the main threat to Build (see risk).

## Slide 7
Week-10 gate: GO only if all three conditions hold
Every condition must pass; any single failure means HOLD
1 · Measured uptime ≥ 99.6%
Option C reference is 99.9%, but reference uptime is not proof; it must be measured in validation
2 · All sites pass capacity validation
Today West fails: demand 338 vs capacity 330 units/day (−8)
3 · Training and validation both finish
Both run weeks 6–8 after Build; the gate sits in week 10
ALL THREE
MET?
YES → GO
Proceed to rollout, weeks 11–14
NO → HOLD
Fix any unmet condition, re-test, re-gate
Reference uptime is not proof of operational performance: the 99.6% test uses measured uptime from validation, not the 99.9% reference figure.

## Slide 8
Supplier delay is the top risk: pre-order critical parts
↑ IMPACT (1–5)
5
4
3
2
1
1
2
3
4
5
LIKELIHOOD (1–5) →
Supplier
delay
Training
gap
Risk (L, I) | Score = L × I | Mitigation
Supplier delay (L4, I3) | 4 × 3 = 12 | Pre-order critical parts to protect Build (W3–5)
Training gap (L2, I4) | 2 × 4 = 8 | Supervised practice during Train (W6–8)
Priority | 12 > 8: act on supplier delay first | Training gap: lower likelihood, higher impact (4)