## Slide 1
CAPITAL ALLOCATION · EQUIPMENT INVESTMENT CHOICE
DECISION: SELECT OPTION B
Option B selected from three reference equipment options (A, B, C). All figures are synthetic.
$343k
Investment
One-time capital
$113k
Annual saving
Per year
3.0 yrs
Simple payback
$343k ÷ $113k/yr
−$4k
Three-year net
3 × $113k − $343k
Context: B is the mid-cost option. Option A has a shorter payback (2.7 yrs) and a positive three-year net (+$19k); Option C has the highest reference uptime (99.9%). Rollout remains conditional on the week-9 gate: measured uptime ≥ 99.6% (B reference: 99.1%), capacity validation at all sites, and completed training and validation.

## Slide 2
OPTIONS: COST, SAVING AND UPTIME
B sits mid-range on cost and saving; A pays back fastest; C has the highest reference uptime.
Metric | Option A | Option B | Option C
Investment ($k) | 197 | 343 | 499
Annual saving ($k/yr) | 72 | 113 | 162
Reference uptime (%) | 97.8 | 99.1 | 99.9
Simple payback (yrs) | 2.7 | 3.0 | 3.1
Three-year net ($k) | +19 | −4 | −13
Investment vs annual saving ($k)
Chart: 
| A | B | C
Investment ($k) | 197 | 343 | 499
Annual saving ($k/yr) | 72 | 113 | 162
Payback = investment ÷ annual saving. Three-year net = 3 × annual saving − investment. Reference options stay unchanged; uptime values are reference figures, not proof of operational performance.

## Slide 3
PERFORMANCE: 270 UNITS BELOW TARGET
Six-month output reached 6,330 vs a 6,600 target; the gap came from M1 and M2.
Monthly output vs target (units)
Chart: 
| M1 | M2 | M3 | M4 | M5 | M6
Actual output | 860 | 790 | 1190 | 1190 | 1130 | 1170
Target | 1100 | 1100 | 1100 | 1100 | 1100 | 1100
ACTUAL TOTAL
6,330 units
TARGET TOTAL
6,600 units
SHORTFALL
−270 units
−4.1% vs target. M1 (−240) and M2 (−310) fell short; M3–M6 exceeded target by +280 combined.

## Slide 4
SCENARIO: OPTION B SAVING SENSITIVITY
Investment held at $343k; annual saving flexed to 80% / 100% / 120% of $113k.
Annual saving by scenario ($k/year)
Chart: 
| Downside (80%) | Base (100%) | Upside (120%)
Annual saving ($k/yr) | 90.4 | 113 | 135.6
Scenario | Saving ($k/yr) | Payback (yrs) | 3-yr net ($k)
Downside (80%) | 90.4 | 3.8 | −71.8
Base (100%) | 113.0 | 3.0 | −4.0
Upside (120%) | 135.6 | 2.5 | +63.8
Payback = $343k ÷ saving
Three-year net = 3 × saving − $343k
Break-even three-year net requires saving of $114.3k/yr ($343k ÷ 3), just above the base case. Only the upside scenario returns a positive three-year net.

## Slide 5
CAPACITY: NO SITE DEMAND ABOVE CAPACITY
Demand above capacity: none. West is tightest at 96.7% utilization (11 units/day headroom).
Site | Daily demand | Daily capacity | Headroom | Utilization | Demand > capacity?
North | 223 | 240 | +17 | 92.9% | No
East | 277 | 310 | +33 | 89.4% | No
West | 319 | 330 | +11 | 96.7% | No
Headroom = capacity − demand; utilization = demand ÷ capacity (units/day). Current headroom is not a substitute for the capacity validation required at the week-9 gate.
Daily demand vs capacity (units/day)
Chart: 
| North | East | West
Daily demand | 223 | 277 | 319
Daily capacity | 240 | 310 | 330

## Slide 6
ROADMAP: 13 WEEKS TO ROLLOUT
Validate and Train run in parallel (weeks 6–8) after Build; both feed the week-9 gate.
TECHNICAL
PEOPLE
Design
Wk 1–2
Build
Wk 3–5
Validate
Wk 6–8
Train
Wk 6–8
Gate
Wk 9
Rollout
Wk 10–13
Wk 1
Wk 3
Wk 6
Wk 9
Wk 13
Rollout starts only after a GO at the week-9 gate. Validate and Train must both finish in weeks 6–8 for the gate to proceed.

## Slide 7
GATE: GO ONLY IF ALL THREE CRITERIA PASS
Week-9 decision. Any unmet criterion results in HOLD.
1. Uptime ≥ 99.6% (measured)
Option B reference uptime is 99.1%. Reference uptime is not proof of operational performance.
2. All sites pass capacity validation
North, East and West each validated; current demand is within capacity at all three.
3. Training and validation both finish
Both parallel workstreams (weeks 6–8) complete before the week-9 gate.
ALL THREE
MET?
YES → GO
Proceed to rollout, weeks 10–13
NO → HOLD
Remediate the unmet criterion, then re-assess

## Slide 8
RISK: SUPPLIER DELAY SCORES HIGHEST (4 × 3 = 12)
IMPACT (1–5) ↑
1
2
3
4
5
1
2
3
4
5
LIKELIHOOD (1–5) →
Supplier delay
L4 · I3
Training gap
L2 · I4
Risk | Likelihood | Impact | Score (L×I) | Mitigation
Supplier delay | 4 | 3 | 12 | Pre-order critical parts
Training gap | 2 | 4 | 8 | Supervised practice