## Slide 1
01 • DECISION
EXECUTIVE REVIEW
Select option B
Strategic equipment procurement — the recommended path and its headline economics
INVESTMENT
$366k
upfront capital
ANNUAL SAVING
$122k
per year
SIMPLE PAYBACK
3.0 years
366 ÷ 122 = 3.0
THREE-YEAR NET
$0k
3 × 122 − 366 = 0
Decision: proceed with option B — subject to the Week-9 gate on slide 7. Break-even is reached at year 3 on base-case savings.
All data are synthetic. Amounts in $k unless stated otherwise.

## Slide 2
02 • OPTIONS
Three paths, one balanced choice
Option B sits between A and C on investment, saving and reference uptime.
Metric | Option A | Option B — SELECTED | Option C
Investment ($k) | 214 | 366 | 528
Annual saving ($k / year) | 79 | 122 | 173
Uptime (%) — reference | 97.8 | 99.1 | 99.9
Simple payback (years) = investment ÷ saving | 2.7 | 3.0 | 3.1
Three-year net ($k) = 3 × saving − investment | +23 | 0 | −9
A: lowest cost, fastest payback — lowest reference uptime (97.8%).
B: +1.3 pts uptime vs A, $162k less than C. Break-even at year 3.
C: highest saving and uptime — highest investment ($528k).
Reference options stay unchanged. Payback and three-year net are computed from the figures above.

## Slide 3
03 • PERFORMANCE
Output trails target by 910 units
Six months of output against a flat 1,100-unit monthly target.
Monthly output vs target (units)
Chart: 
| M1 | M2 | M3 | M4 | M5 | M6
Actual output | 740 | 780 | 1120 | 1030 | 1110 | 910
Target | 1100 | 1100 | 1100 | 1100 | 1100 | 1100
ACTUAL TOTAL
5,690 units
TARGET TOTAL
6,600 units (6 × 1,100)
SHORTFALL
910 units • 86.2% of target
Only M3 (1,120) and M5 (1,110) met the 1,100-unit target. Shortfall = 6,600 − 5,690 = 910 units.
Units: equipment output per month. All data are synthetic.

## Slide 4
04 • SCENARIO
Option B breaks even at base case
Sensitivity of the $122k annual saving at 80% / 100% / 120% — investment held at $366k.
Annual saving by scenario ($k / year)
Chart: 
| Downside | Base | Upside
Annual saving ($k) | 97.6 | 122 | 146.4
Scenario | Saving ($k/yr) | Payback (yrs) | 3-yr net ($k)
Downside (80%) | 97.6 | 3.75 | −73.2
Base (100%) | 122.0 | 3.00 | 0.0
Upside (120%) | 146.4 | 2.50 | +73.2
Payback = 366 ÷ saving • Three-year net = 3 × saving − 366
Reading: at 80% of expected saving the 3-year net is −$73.2k and payback stretches to 3.75 years; at 120% it is +$73.2k with a 2.50-year payback.
Scenarios are 80% / 100% / 120% of $122k. All data are synthetic.

## Slide 5
05 • CAPACITY
West is above capacity
Daily demand against installed capacity by site.
Site | Demand / day | Capacity / day | Headroom | Utilization | Status
North | 236 | 240 | +4 | 98.3% | Within capacity
East | 294 | 310 | +16 | 94.8% | Within capacity
West | 338 | 330 | −8 | 102.4% | ABOVE CAPACITY
⚠ WEST
Demand exceeds capacity by 8 per day
338 − 330 = 8
Network total: demand 868 vs capacity 880 / day (+12) — the total masks the West constraint.
Headroom = capacity − demand. Utilization = demand ÷ capacity. North has only 4 / day spare.
Units: units per day. All data are synthetic. West must be resolved before capacity validation can pass (slide 7).

## Slide 6
06 • ROADMAP
13-week roadmap, gate at week 9
Technical and People lanes run in parallel after Build. Both Validate and Train feed the gate.
Week 1 Week 9 = GATE Week 13
TECHNICAL
PEOPLE
Design
Wk 1–2
Build
Wk 3–5
Validate
Wk 6–8
Train
Wk 6–8
GATE
Wk 9
Rollout
Wk 10–13
Sequence: Design → Build → (Validate ∥ Train, weeks 6–8) → Gate (week 9) → Rollout (weeks 10–13). No rollout before the gate decision.
Bars are positioned to week scale (weeks 1–13). All data are synthetic.

## Slide 7
07 • GATE
GO only if every criterion passes
Week-9 gate criteria — all three must be met. Otherwise the decision is HOLD.
1 • Uptime at least 99.6%
Measured operational uptime — threshold: ≥ 99.6%
2 • All sites pass capacity validation
North, East and West — no site above capacity
3 • Training AND validation both finish
Both parallel tracks complete (weeks 6–8)
GO → Rollout (Wk 10–13)
only if 1 AND 2 AND 3 pass
HOLD
if any criterion fails or is unproven
Caveat: reference uptime is not proof of operational performance. Option B's 99.1% reference figure does not by itself establish the ≥ 99.6% gate — measured evidence is required.
Gate at week 9, before rollout weeks 10–13. All data are synthetic.

## Slide 8
08 • RISK
Two risks, mitigations assigned
Likelihood (x) and impact (y), each scored 1–5.
Impact ↑
S
T
1 2 3 4 5 Likelihood →
5
4
3
2
1
Risk | L | I | L × I | Mitigation
S — Supplier delay | 4 | 3 | 12 | Pre-order critical parts
T — Training gap | 2 | 4 | 8 | Supervised practice
Priority: Supplier delay scores highest (4 × 3 = 12) — act first with pre-orders. Training gap (2 × 4 = 8) is lower-likelihood but higher impact if it occurs.
L = likelihood (1–5), I = impact (1–5), plotted at (L, I): S = (4, 3), T = (2, 4). All data are synthetic.