## Slide 1
EQUIPMENT INVESTMENT • CAPITAL ALLOCATION
1 — DECISION
SELECT OPTION C
Approve Option C for the gated roadmap.
Proceed to rollout only if the Week 10 gate is met (Slide 7). Options A and B remain unchanged reference alternatives.
WHY THIS NEEDS SCRUTINY
Highest investment and highest saving. Payback is just over 3 years and the 3-year net is negative, so the case depends on full saving delivery and on demonstrated gate performance.
INVESTMENT
$499k
ANNUAL SAVING
$162k / year
SIMPLE PAYBACK
3.1 years
3-YEAR NET
−$13k
Simple payback = 499 ÷ 162 = 3.08 yrs • 3-year net = 3 × 162 − 499 = −$13k • All data are synthetic.
1 / 8

## Slide 2
NEUTRAL COMPARISON • REFERENCE OPTIONS UNCHANGED
2 — OPTIONS
Metric | Option A | Option B | Option C ★
Investment ($k) | 197 | 343 | 499
Annual saving ($k/yr) | 72 | 113 | 162
Reference uptime (%) | 97.8 | 99.1 | 99.9
Payback (yrs) = inv. ÷ saving | 2.74 | 3.04 | 3.08
3-year net ($k) = 3×saving − inv. | +19 | −4 | −13
INVESTMENT vs ANNUAL SAVING ($k)
Chart: 
| A | B | C
Investment ($k) | 197 | 343 | 499
Annual saving ($k) | 72 | 113 | 162
READ-OUT: A is cheapest, fastest payback and the only 3-year positive. C (selected ★) costs $156k more than B for +$49k/yr saving and +0.8 pts uptime; vs A, +$302k for +$90k/yr and +2.1 pts.
Reference uptime is supplier/reference data — it is not proof of operational performance.
2 / 8

## Slide 3
SIX-MONTH OUTPUT vs TARGET
3 — PERFORMANCE
MONTHLY OUTPUT AND TARGET (units / month)
Chart: 
| M1 | M2 | M3 | M4 | M5 | M6
Output (units) | 860 | 790 | 1190 | 1350 | 1130 | 1170
Target (units) | 1100 | 1100 | 1100 | 1100 | 1100 | 1100
TOTALS (M1–M6)
Actual: 6,490 units
Target: 6,600 units
Shortfall: 110 units
110 ÷ 6,600 = 1.7% below target.
M1 −240, M2 −310; then M3 +90, M4 +250, M5 +30, M6 +70.
CONCLUSION: Strong recovery from M3 — led by M4 (1,350) — but the half-year still closed 110 units (1.7%) short.
3 / 8

## Slide 4
OPTION C • INVESTMENT $499k • SENSITIVITY TO SAVING
4 — SCENARIO
ANNUAL SAVING BY SCENARIO ($k / year)
Chart: 
| Downside 80% | Base 100% | Upside 120%
Annual saving ($k) | 129.6 | 162 | 194.4
COMPUTED PAYBACK AND 3-YEAR NET
Scenario | Saving ($k/yr) | Payback (yrs) | 3-yr net ($k)
Downside (80%) | 129.6 | 3.85 | −110.2
Base (100%) | 162.0 | 3.08 | −13.0
Upside (120%) | 194.4 | 2.57 | +84.2
Payback = 499 ÷ saving
3-year net = 3 × saving − 499
Break-even saving for 3-yr net = $0: 499 ÷ 3 = $166.3k/yr
CONCLUSION: Only the upside case is 3-year positive (+$84.2k). Base is −$13k; a 20% saving shortfall widens the loss to −$110.2k and payback to 3.9 years.
4 / 8

## Slide 5
DAILY DEMAND vs CAPACITY BY SITE
5 — CAPACITY
Site | Demand / day | Capacity / day | Headroom | Demand > capacity?
North | 223 | 240 | 17 | No
East | 277 | 310 | 33 | No
West | 319 | 330 | 11 | No
Headroom = capacity − demand.
Utilisation: North 92.9% • East 89.4% • West 96.7%
No site has demand above capacity — but West has only 11 units/day spare.
DEMAND vs CAPACITY (units / day)
Chart: 
| North | East | West
Daily demand | 223 | 277 | 319
Capacity | 240 | 310 | 330
WATCH: WEST — 319 / 330. Any growth or downtime erases headroom first.
All six demand/capacity cells are preserved exactly as given.
5 / 8

## Slide 6
14-WEEK PLAN • VALIDATE AND TRAIN IN PARALLEL AFTER BUILD
6 — ROADMAP
Wk 1 2 3 4 5 6 7 8 9 10 11 12 13 14
TECHNICAL
Design 1–2
Build 3–5
Validate 6–8
PEOPLE
Train 6–8
GATE
Wk 10
Rollout
Weeks 11–14
SEQUENCE: Design (1–2) → Build (3–5) → Validate (6–8) and Train (6–8) in parallel → Gate (Week 10) → Rollout (11–14).
Both Validate and Train feed the gate. Neither lane can bypass it. Week 9 sits between parallel work and the gate.
6 / 8

## Slide 7
WEEK 10 • ALL CONDITIONS MUST HOLD
7 — GATE
1 UPTIME
Operational uptime ≥ 99.6%
Option C reference uptime is 99.9% (+0.3 pts vs threshold) — but reference data is not proof.
2 CAPACITY VALIDATION
All sites pass capacity validation
North, East and West — no exceptions. West headroom is thinnest (11/day).
3 COMPLETION
Training AND validation both finish
Both Week 6–8 lanes must be complete before the gate can pass.
GO → ROLLOUT (WEEKS 11–14)
Only if conditions 1, 2 and 3 are all met.
HOLD → NO ROLLOUT
If any single condition fails.
CAVEAT: Reference uptime is not proof of operational performance. Uptime must be demonstrated in operation at ≥99.6%.
7 / 8

## Slide 8
LIKELIHOOD × IMPACT • EACH SCALE 1–5
8 — RISK
Supplier delay (4, 3)
Training gap (2, 4)
1 2 3 4 5
LIKELIHOOD →
5
4
3
2
1
IMPACT ↑
Risk | L × I = Score | Mitigation
Supplier delay | 4 × 3 = 12 | Pre-order critical parts
Training gap | 2 × 4 = 8 | Supervised practice
PRIORITY: Supplier delay scores highest (12) — pre-order early. Training gap is less likely but higher impact (4) — it directly threatens the Week 10 gate.
DECISION REMINDER: Select Option C ($499k, $162k/yr, 3.1-yr payback, −$13k 3-year net), gated at Week 10. All data are synthetic.
8 / 8