## Slide 1
DECISION: SELECT OPTION B
Requested approval: $343k equipment investment, subject to the week-9 GO/HOLD gate (synthetic data)
$343k
Investment (one-time)
$113k
Annual saving per year
3.0 yrs
Simple payback (343 ÷ 113)
−$4k
Three-year net (3 × 113 − 343)
WHAT OPTION B DELIVERS
Mid-range option: higher saving than A ($72k/yr), lower investment than C ($499k). Reference uptime 99.1%.
THREE-YEAR VIEW
Base case is near breakeven at −$4k after three years; downside −$71.8k, upside +$63.8k (see Scenario).
CONDITION
Rollout proceeds only on GO at week 9: uptime ≥ 99.6%, all sites pass capacity validation, training and validation complete.
All figures are synthetic. $k = thousands of dollars.

## Slide 2
OPTIONS: THREE REFERENCE CONFIGURATIONS
Investment, annual saving and reference uptime as provided; reference options unchanged
Investment and annual saving by option ($k)
Chart: 
| Option A | Option B | Option C
Investment ($k) | 197 | 343 | 499
Annual saving ($k/yr) | 72 | 113 | 162
Side-by-side metrics
Metric | A | B | C
Investment ($k) | 197 | 343 | 499
Annual saving ($k/yr) | 72 | 113 | 162
Reference uptime (%) | 97.8 | 99.1 | 99.9
Simple payback (yrs) | 2.7 | 3.0 | 3.1
Three-year net ($k) | +19 | −4 | −13
Payback = investment ÷ annual saving; three-year net = 3 × saving − investment. Only C's reference uptime meets the 99.6% gate threshold; reference uptime is not proof of operational performance.

## Slide 3
PERFORMANCE: 270 UNITS BELOW SIX-MONTH TARGET
Monthly output M1–M6 versus a flat target of 1,100 units per month
Monthly output vs target (units)
Chart: 
| M1 | M2 | M3 | M4 | M5 | M6
Actual output | 860 | 790 | 1190 | 1190 | 1130 | 1170
Target | 1100 | 1100 | 1100 | 1100 | 1100 | 1100
6,330
Actual total (units)
6,600
Target total (units)
−270
Shortfall (units, −4.1%)
Variance vs target: M1 −240, M2 −310, M3 +90, M4 +90, M5 +30, M6 +70. Early deficit of 550 is offset by 280 surplus → net −270.

## Slide 4
SCENARIO: PAYBACK RANGES FROM 2.5 TO 3.8 YEARS
Option B, investment fixed at $343k; saving at 80% / 100% / 120% of $113k per year
Annual saving by scenario ($k/year)
Chart: 
| Downside (80%) | Base (100%) | Upside (120%)
Annual saving ($k/yr) | 90.4 | 113 | 135.6
Computed payback and three-year net
Scenario | Saving ($k/yr) | Payback (yrs) | 3-yr net ($k)
Downside | 90.4 | 343 ÷ 90.4 = 3.8 | 3 × 90.4 − 343 = −71.8
Base | 113.0 | 343 ÷ 113 = 3.0 | 3 × 113 − 343 = −4.0
Upside | 135.6 | 343 ÷ 135.6 = 2.5 | 3 × 135.6 − 343 = +63.8
BREAKEVEN WITHIN THREE YEARS
Requires saving ≥ 343 ÷ 3 = $114.3k/yr, about 1% above the base case. Only the upside scenario clears it.

## Slide 5
CAPACITY: NO SITE HAS DEMAND ABOVE CAPACITY
Daily demand vs daily capacity at North, East and West; West has the tightest margin
Daily demand vs capacity by site (per day)
Chart: 
| North | East | West
Daily demand | 223 | 277 | 319
Daily capacity | 240 | 310 | 330
Site check
Site | Demand / day | Capacity / day | Headroom | Utilization | Demand > capacity?
North | 223 | 240 | 17 | 92.9% | No
East | 277 | 310 | 33 | 89.4% | No
West | 319 | 330 | 11 | 96.7% | No
RESULT
Demand is within capacity at all three sites. West runs closest to its limit (96.7%, 11/day headroom). Site capacity validation remains a gate criterion.
Headroom = capacity − demand; utilization = demand ÷ capacity.

## Slide 6
ROADMAP: 13 WEEKS FROM DESIGN TO ROLLOUT
Technical and People lanes converge at the week-9 gate (drawn to scale)
TECHNICAL
PEOPLE
Design
Weeks 1–2
Build
Weeks 3–5
Validate
Weeks 6–8
Train
Weeks 6–8
Gate
Wk 9
Rollout
Weeks 10–13
Validate and Train run in parallel in weeks 6–8, both starting after Build. Both must finish before the week-9 gate; rollout (weeks 10–13) starts only on GO.

## Slide 7
GATE: GO ONLY IF ALL THREE CRITERIA ARE MET
Week-9 decision rule; any unmet criterion results in HOLD
Criterion | Threshold for GO | Evidence at week 9
Uptime | At least 99.6% | Measured operational uptime, not the reference figure
Capacity | All sites pass (North, East, West) | Capacity validation result for each site
Readiness | Training and validation both finished | Completion of the weeks 6–8 workstreams
GO
All three criteria met → proceed to rollout, weeks 10–13
HOLD
Any criterion unmet → no rollout until resolved and re-tested
CAVEAT
Reference uptime is not proof of operational performance. Option B's reference uptime (99.1%) is 0.5 points below the 99.6% threshold, so GO depends on measured operational uptime.

## Slide 8
RISK: SUPPLIER DELAY IS THE MORE LIKELY RISK
Likelihood (x) and impact (y), each scored 1–5, with planned mitigations
Impact (1–5) ↑
1
2
3
4
5
1
2
3
4
5
Likelihood (1–5) →
Supplier delay (L4, I3)
Training gap (L2, I4)
Risk | L | I | L × I | Mitigation
Supplier delay | 4 | 3 | 12 | Pre-order critical parts
Training gap | 2 | 4 | 8 | Supervised practice
READING THE MATRIX
Supplier delay is more likely (4 vs 2) and scores higher overall (12 vs 8). Training gap carries the higher impact (4 vs 3). Score = likelihood × impact, used as a ranking aid.
All data are synthetic.