## Slide 1
RECOMMENDATION: SELECT OPTION B
Equipment investment decision | Board capital allocation | All data synthetic
SELECT OPTION B
A balanced investment: materially higher saving than A, without the $499k commitment of C.
DECISION ASK
Approve $343k for Option B, subject to the Week 9 gate (Slide 7).
$343k
Investment (one-time)
$113k
Annual saving
3.0 yrs
Simple payback 343 / 113
$-4k
3-year net 3x113 - 343
Interpretation: Option B is near break-even by year 3 (-$4k) and positive thereafter if savings persist. This deck tests that case against performance, capacity, downside and delivery risk before rollout.
1 DECISION

## Slide 2
OPTIONS: B SITS BETWEEN LOW COST AND MAXIMUM
UPTIME
Reference options stay unchanged | Payback = investment / saving | 3-yr net = 3 x saving - investment
Option | Investment ($k) | Saving ($k/yr) | Uptime (%) | Payback (yr) | 3-yr net ($k)
A | 197 | 72 | 97.8 | 2.7 | +19
B SELECTED | 343 | 113 | 99.1 | 3.0 | -4
C | 499 | 162 | 99.9 | 3.1 | -13
READING THE TRADE-OFF
• A is cheapest and pays back fastest, but saving and uptime are lowest.
• B adds $41k/yr saving over A for $146k more capital; uptime +1.3 pts.
• C adds a further $49k/yr over B for $156k more; uptime +0.8 pts.
INVESTMENT vs ANNUAL SAVING ($k)
Chart: 
| A | B | C
Investment ($k) | 197 | 343 | 499
Saving ($k/yr) | 72 | 113 | 162
B: step-up in saving without C-level capital.
2 OPTIONS

## Slide 3
PERFORMANCE: OUTPUT RECOVERED, BUT 6-MONTH TOTAL
FELL SHORT
Monthly output vs fixed target of 1,100 units | Units per month
Chart: 
| M1 | M2 | M3 | M4 | M5 | M6
Actual output | 860 | 790 | 1190 | 1190 | 1130 | 1170
Target | 1100 | 1100 | 1100 | 1100 | 1100 | 1100
6,330
Actual total (units)
6,600
Target total (units)
-270
Shortfall (units) 96% of target
M1-M2 missed target by 240 and 310 units. M3-M6 exceeded target in every month, recovering most — but not all — of the early gap.
3 PERFORMANCE

## Slide 4
SCENARIO: B NEEDS ~BASE SAVING TO CLEAR 3-YEAR
BREAK-EVEN
Option B investment $343k | Saving at 80% / 100% / 120% of $113k per year
ANNUAL SAVING BY SCENARIO ($k/yr)
Chart: 
| Downside 80% | Base 100% | Upside 120%
Annual saving ($k) | 90.4 | 113 | 135.6
Scenario | Saving ($k/yr) | Payback (yr) | 3-yr net ($k)
Downside (80%) | 90.4 | 3.8 | -71.8
Base (100%) | 113.0 | 3.0 | -4.0
Upside (120%) | 135.6 | 2.5 | +63.8
ARITHMETIC
Payback = 343 / saving
3-year net = 3 x saving - 343
Break-even saving = 343 / 3 = $114.3k/yr
Downside leaves a $71.8k three-year gap. Protecting base-case saving is the financial priority.
4 SCENARIO

## Slide 5
CAPACITY: NO SITE EXCEEDS CAPACITY — WEST IS
TIGHTEST
Daily demand vs daily capacity (units/day) | Headroom = capacity - demand
Site | Demand | Capacity | Headroom | Utilisation | Status
North | 223 | 240 | +17 | 92.9% | Within
East | 277 | 310 | +33 | 89.4% | Within
West | 319 | 330 | +11 | 96.7% | Within — tight
FINDING
No site has demand above capacity.
West has only 11 units/day spare (3.3% of capacity), so small demand growth or downtime would breach it first. Prioritise West in capacity validation.
DEMAND vs CAPACITY (units/day)
Chart: 
| North | East | West
Demand | 223 | 277 | 319
Capacity | 240 | 310 | 330
5 CAPACITY

## Slide 6
ROADMAP: VALIDATE AND TRAIN RUN IN PARALLEL TO THE
WEEK 9 GATE
13-week plan | Both Validate and Train feed the gate before rollout
Wk 1 2 3 4 5 6 7 8 9 10 11 12 13
TECHNICAL
Design 1-2
Build 3-5
Validate 6-8
PEOPLE
Train 6-8
GATE
Wk 9
Rollout 10-13
Sequence: Design (1-2) -> Build (3-5) -> Validate and Train in parallel (6-8) -> Gate (9) -> Rollout (10-13). No rollout before both parallel streams finish and pass the gate.
6 ROADMAP

## Slide 7
GATE: GO ONLY IF ALL FOUR CONDITIONS ARE MET
Week 9 decision | Any unmet condition means HOLD — no partial rollout
GO CRITERIA (ALL REQUIRED)
1. Uptime at least 99.6% — demonstrated in operation
2. All sites pass capacity validation (North, East, West)
3. Validation finished (Technical lane)
4. Training finished (People lane)
GO
All four met -> proceed to rollout, weeks 10-13.
HOLD
Otherwise hold, remediate, and re-test. Do not roll out.
Caveat: Option B reference uptime (99.1%) is not proof of operational performance and is below this 99.6% threshold — it must be demonstrated at the gate.
7 GATE

## Slide 8
RISK: SUPPLIER DELAY IS LIKELIER; TRAINING GAP HITS
HARDER
Likelihood (x) and impact (y), each scored 1-5 | Higher and further right = greater exposure
IMPACT
5
4
3
2
1
Supplier delay
Training gap
1 2 3 4 5 LIKELIHOOD ->
Risk | Likelihood | Impact | Score (LxI)
Supplier delay | 4 | 3 | 12
Training gap | 2 | 4 | 8
MITIGATIONS
Supplier delay (4 x 3): pre-order critical parts.
Training gap (2 x 4): supervised practice.
Both mitigations should be in place before the Week 9 gate.
Board action: approve Option B ($343k) with mitigations funded and rollout conditional on the Week 9 GO gate.
8 RISK