## Slide 1
ASTER COLD-CHAIN / OPERATIONS COMMITTEE
Choose Resilient: uptime now outranks price
Approve $440k for regional distribution capacity. Resilient offers 99.8% reference uptime; release rollout only after the week-10 gate.
$440k
Investment
$155k
Annual saving
2.8 years
Simple payback
$25k
Three-year net saving
Higher uptime earns the premium; readiness still needs proof
Versus Balanced: $90k more investment and $25k more annual saving. Require all gate thresholds to pass before rollout in weeks 11–14.
All data synthetic • Currency $k • Payback = investment ÷ annual saving • Three-year net = 3 × saving − investment
1 / 8

## Slide 2
M4 beats target; the six-month shortfall is 520 shipments
Six-month throughput • shipments • all 12 monthly values shown
Chart: 
| M1 | M2 | M3 | M4 | M5 | M6
Actual | 870 | 850 | 720 | 1080 | 720 | 910
Target | 950 | 970 | 840 | 1040 | 820 | 1050
TOTAL ACTUAL
5,150
TOTAL TARGET
5,670
SHORTFALL
520
shipments
Synthetic data • Shortfall = total target − total actual • Monthly totals are separate from daily site demand and capacity.
2 / 8

## Slide 3
Resilient alone has reference uptime above the gate
Reference options • all prices, savings, uptime and lead times remain unchanged
Option | Investment $k | Saving $k/yr | Uptime % | Lead weeks
Lean | 220 | 95 | 97.5 | 6
Balanced | 350 | 130 | 99.0 | 8
Resilient | 440 | 155 | 99.8 | 10
Selected: Resilient
99.8% reference uptime exceeds the ≥99.5% gate. Balanced is 99.0%; Lean is 97.5%.
Tradeoff versus Balanced
$90k more investment and 2 more lead weeks buy 0.8 percentage points of uptime and $25k/yr more saving.
Synthetic data • Currency $k • Reference uptime supports selection; measured compliance is required at the week-10 gate.
3 / 8

## Slide 4
A 20% savings downside turns three-year net negative
Resilient sensitivity • fixed investment of $440k • annual saving in $k
Chart: 
| Downside 80% | Base 100% | Upside 120%
Annual saving $k | 124 | 155 | 186
Returns at each savings level
Scenario | Payback years | 3-year net $k
Downside | 3.5 | −68
Base | 2.8 | 25
Upside | 2.4 | 118
Downside net saving is −$68k over three years; the base case yields $25k.
Synthetic data • Payback = 440 ÷ annual saving, rounded to 1 decimal • Three-year net = 3 × annual saving − 440
4 / 8

## Slide 5
South is capacity-constrained despite network headroom
Daily site demand and capacity • current on-time performance and accountable owners
Site | Demand/day | Capacity/day | On time % | Owner
North | 340 | 380 | 95 | Ari
Central | 290 | 330 | 94 | Bo
South | 340 | 320 | 89 | Cy
East | 320 | 340 | 94 | Dee
West | 310 | 340 | 96 | Eli
Demand: 1,600/day
Capacity: 1,710/day
Headroom: 110/day
South has a 20/day deficit. Central, South and East are below the ≥95% on-time gate.
Synthetic data • Capacity-constrained means demand exceeds capacity • Daily figures are separate from six-month shipment totals.
5 / 8

## Slide 6
Validate and Train must both clear the week-10 gate
Delivery dependencies flow left to right • weeks from approval • rollout follows Gate GO
Technical
People
Design
Weeks 1–2
Build
Weeks 3–5
Validate
Weeks 6–8
Train
Weeks 6–8
Decision gate
Week 10
Rollout
Weeks 11–14
Design has no prerequisite. Build enables Validate and Train; both feed the gate. Gate GO enables Rollout.
Synthetic plan • Activity boxes show scheduled weeks, not a scaled time axis • Gate thresholds appear on slide 8.
6 / 8

## Slide 7
R2 and R5 have maximum impact; R1 is most likely
All five risks are plotted at their stated scores and paired with a mitigation
Impact ↑ (1–5)
Likelihood → (1–5)
Impact | 1 | 2 | 3 | 4 | 5
5 |  | R2 | R5 |  | 
4 |  |  | R3 |  | 
3 |  |  |  | R1 | 
2 |  | R4 |  |  | 
1 |  |  |  |  | 
Mitigation for every risk
Risk ID | Mitigation
R1 | Cross-train two crews
R2 | Dual-source hardware
R3 | Test failover weekly
R4 | Audit labels
R5 | Test backup power before gate
Synthetic risk assessment • Likelihood increases to the right; impact increases upward • IDs mark the scored coordinates.
7 / 8

## Slide 8
Approve $440k for Resilient; decide rollout at week 10
Fund the selected investment now. At week 10, require completed Validate AND Train plus every threshold below before GO.
WEEK 10 / ALL THREE CONDITIONS REQUIRED
1 Uptime ≥99.5%
2 All five sites ≥95% on time
3 Backup-power test passed
GO: every threshold passes
Proceed to the next rollout
Weeks 11–14
HOLD: any threshold fails
Hold rollout, remediate and revalidate before a new GO decision.
Current on-time gaps: Central 94%, South 89%, East 94%. Verify uptime and backup power at the gate.
Synthetic decision case • Investment $440k • Annual saving $155k • Payback 2.8 years • Three-year net saving $25k
8 / 8