## Slide 1
Recommend Resilient: $440k buys $155k/yr in savings and
99.8% rated uptime
Aster cold-chain · regional distribution capacity · operations committee decision
$440k
Investment (Resilient)
$155k/yr
Annual saving
2.8 yrs
Payback (440 ÷ 155)
$25k
3-yr net (3×155 − 440)
Why act now
• 520 shipments below target in six months (5,150 vs 5,670)
• South demand of 340/day exceeds its 320/day capacity
• Only Resilient is rated above the 99.5% uptime gate
• Costs $90k more than Balanced; saves $25k/yr more
DECISION REQUESTED
Fund $440k for Resilient now; release the week 11–14 rollout only on a GO at the week-10 gate.
Gate: uptime ≥99.5%, all five sites ≥95% on time, backup-power test passed. Any miss → HOLD.

## Slide 2
Shipments ran 520 below target over six months: 5,150 actual
vs 5,670
Monthly shipments, actual vs target, M1–M6 (M4 actual corrected to 1,080)
Shipments per month
Chart: 
| M1 | M2 | M3 | M4 | M5 | M6
Actual | 870 | 850 | 720 | 1080 | 720 | 910
Target | 950 | 970 | 840 | 1040 | 820 | 1050
5,150
Total actual shipments
5,670
Total target shipments
−520
Gap (9.2% below target)
Five of six months missed target (shortfall 80–140); only M4 beat target, by 40.

## Slide 3
Resilient costs $90k more than Balanced but is the only option
rated above the 99.5% uptime gate
Reference values unchanged · payback = investment ÷ annual saving · 3-yr net = 3 × saving − investment
Option | Investment $k | Saving $k/yr | Uptime % | Lead weeks | Payback yrs | 3-yr net $k
Lean | 220 | 95 | 97.5 | 6 | 2.3 | 65
Balanced | 350 | 130 | 99.0 | 8 | 2.7 | 40
Resilient (selected) | 440 | 155 | 99.8 | 10 | 2.8 | 25
Why not Lean
Best payback (2.3 yrs) and net ($65k), but 97.5% uptime is 2 points below the gate.
Why not Balanced
Rated 99.0% uptime is 0.5 pt short of the gate; GO would rely on beating its rating.
Tradeoff we accept
Lowest 3-yr net ($25k) and a 10-week lead, so the gate moves to week 10.

## Slide 4
Base case nets $25k over three years; an 80% downside loses
$68k
Annual saving at 80/100/120% of Resilient's $155k; investment fixed at $440k
Annual saving, $k
Chart: 
| Downside 80% | Base 100% | Upside 120%
Annual saving $k | 124 | 155 | 186
Scenario | Saving $k/yr | Payback yrs | 3-yr net $k
Downside 80% | 124 | 3.5 | −68
Base 100% | 155 | 2.8 | 25
Upside 120% | 186 | 2.4 | 118
Three-year breakeven needs ≈$147k/yr saving (≈95% of base). A shortfall above 5% means no payback within three years.

## Slide 5
South is the only capacity-constrained site: 340/day demand vs
320 capacity
Daily demand and capacity by site; three sites are also below the 95% on-time gate
Site | Demand/day | Capacity/day | Headroom | On time % | Owner
North | 340 | 380 | +40 | 95 | Ari
Central | 290 | 330 | +40 | 94 | Bo
South | 340 | 320 | −20 | 89 | Cy
East | 320 | 340 | +20 | 94 | Dee
West | 310 | 340 | +30 | 96 | Eli
Total | 1,600 | 1,710 | +110 | — | —
Below 95% on time: Central 94%, South 89%, East 94%. All must reach 95% by the week-10 gate.
1,600
Total demand per day
1,710
Total capacity per day
CAPACITY-CONSTRAINED
South (owner Cy): short 20/day, 340 demand vs 320 capacity

## Slide 6
Rollout begins week 11 only after Validate and Train both clear
the week-10 gate
14-week plan in two lanes plus decision gate; connectors show dependencies
Week 1
Week 10 gate
Week 14
Technical
Decision
People
Design wk 1–2
Build wk 3–5
Validate wk 6–8
Rollout wk 11–14 (GO)
Train wk 6–8
GATE
wk 10
Dependencies: Design → Build → Validate; Build → Train; Validate AND Train → Gate (wk 10); Gate GO → Rollout (wk 11–14). No GO = HOLD.

## Slide 7
New risk R5, backup power, now scores highest (15 of 25); R1
and R3 follow at 12
Likelihood × impact on 1–5 scales; each ID sits at its rated coordinates, score in brackets
Likelihood (1 = low, 5 = high) →
Impact (1–5) ↓
I \ L | 1 | 2 | 3 | 4 | 5
5 |  | R2 (10) | R5 (15) |  | 
4 |  |  | R3 (12) |  | 
3 |  |  |  | R1 (12) | 
2 |  | R4 (4) |  |  | 
1 |  |  |  |  | 
ID | L × I | Mitigation
R1 | 4 × 3 = 12 | Cross-train two crews
R2 | 2 × 5 = 10 | Dual-source hardware
R3 | 3 × 4 = 12 | Test failover weekly
R4 | 2 × 2 = 4 | Audit labels
R5 | 3 × 5 = 15 | Test backup power before gate
Act first on R5 before the week-10 gate, then R1 and R3; R2 is unlikely but has maximum impact.

## Slide 8
Decision: fund $440k for Resilient now; GO to the week 11–14
rollout only if all three gate tests pass
Go/no-go at week 10; any failed threshold triggers HOLD
Fund $440k
Build & train wk 1–8
Gate wk 10
GO: rollout wk 11–14
Gate threshold | Required for GO | Current status
Uptime | ≥ 99.5% | Resilient rated 99.8%
On time, all five sites | ≥ 95% each | Central 94, South 89, East 94
Backup-power test | Passed | Test before gate (R5)
IF ANY THRESHOLD FAILS → HOLD
Rollout does not start. Close the failing gap, then re-run the gate.
Ask today: approve $440k for Resilient ($155k/yr saving, 2.8-yr payback, $25k three-year net) and these week-10 gate criteria.