## Slide 1
Recommend Resilient: $155k/yr saving, 2.8-year payback
Aster cold-chain — regional distribution capacity | Operations committee | Synthetic data
DECISION REQUESTED: Approve Resilient option
Invest $440k — uptime now outranks price. Highest reliability (99.8%), subject to the Week 10 go / no-go gate.
$440k
Chosen investment — Resilient
$155k/yr
Annual saving
2.8 years
Simple payback (440 ÷ 155)
$25k
Three-year net saving (3×155 − 440)
Why now: six-month shipments were 520 below target. Resilient targets 99.8% uptime in 10 lead weeks. Funding for rollout is released only if every Week 10 threshold passes; otherwise HOLD. Rollout follows in Weeks 11–14.

## Slide 2
Six months fell 520 shipments short of target
Actual vs target shipments, M1–M6 | All 12 values labelled | Synthetic data
Shipments per month
Chart: 
| M1 | M2 | M3 | M4 | M5 | M6
Actual | 870 | 850 | 720 | 1080 | 720 | 910
Target | 950 | 970 | 840 | 1040 | 820 | 1050
5,150
Total actual shipments
5,670
Total target shipments
520 short
Gap = 5,670 − 5,150 (9.2% below target)
Five of six months missed target; only M4 exceeded it (1,080 vs 1,040). The shortfall is persistent, not a single-month dip.

## Slide 3
Resilient buys highest uptime — at the highest cost
Option comparison — reference values unchanged | Uptime now outranks price
Option | Investment $k | Saving $k/yr | Uptime % | Lead weeks
Lean | 220 | 95 | 97.5 | 6
Balanced | 350 | 130 | 99.0 | 8
Resilient | 440 | 155 | 99.8 | 10
Why Resilient is selected
Best uptime (99.8%) and highest saving ($155k/yr). With uptime ranked above price, it best protects cold-chain reliability.
Tradeoff vs Balanced
+$90k investment and +2 lead weeks buys only +$25k/yr saving and +0.8 pts uptime. Payback slips to 2.8 years; 3-yr net is $25k.

## Slide 4
Base case pays back in 2.8 years; downside is net-negative
Scenarios at 80% / 100% / 120% of Resilient saving | Investment held at $440k
Annual saving, $k/yr
Chart: 
| Downside 80% | Base 100% | Upside 120%
Annual saving $k/yr | 124 | 155 | 186
Scenario | Saving $k/yr | Payback yrs | 3-yr net $k
Downside 80% | 124 | 3.5 | −68
Base 100% | 155 | 2.8 | 25
Upside 120% | 186 | 2.4 | 118
Payback = 440 ÷ saving. Three-year net = 3×saving − 440.
Read: downside is net-negative over three years (−$68k) — the Week 10 gate protects against committing rollout spend into that case.

## Slide 5
South is over capacity today; network headroom is only
110/day
Daily demand and capacity by site (shipments/day) — not six-month totals
Site | Demand/day | Capacity/day | On time % | Owner
North | 340 | 380 | 95 | Ari
Central | 290 | 330 | 94 | Bo
South | 340 | 320 | 89 | Cy
East | 320 | 340 | 94 | Dee
West | 310 | 340 | 96 | Eli
1,600/day
Total daily demand
1,710/day
Total daily capacity
110/day
Network headroom (1,710 − 1,600)
Capacity-constrained site: South — demand 340/day exceeds capacity 320/day by 20/day (106% utilisation), with the lowest on-time rate (89%). All other sites have demand below capacity.

## Slide 6
Gate at Week 10: rollout starts only after Validate and Train
Two-lane roadmap, Weeks 1–14 | Dependencies shown under each activity
Technical
Design
Weeks 1–2
Dep: None
Build
Weeks 3–5
Dep: Design
Validate
Weeks 6–8
Dep: Build
Rollout
Weeks 11–14
Dep: Gate GO
People
Train
Weeks 6–8
Dep: Build
DECISION GATE
Week 10
Gate dependency: Validate AND Train must both complete before the Week 10 gate. Rollout (Weeks 11–14) depends on Gate GO — no GO, no rollout.

## Slide 7
Top risks cluster at high impact: R2, R3 and R5 need mitigation
Risk matrix — likelihood (vertical) by impact (horizontal), each scored 1–5
R1
R2
R3
R4
R5
1 2 3 4 5
IMPACT (1 → 5) →
5
4
3
2
1
LIKELIHOOD ↑
ID | Likelihood 1-5 | Impact 1-5 | Mitigation
R1 | 4 | 3 | Cross-train two crews
R2 | 2 | 5 | Dual-source hardware
R3 | 3 | 4 | Test failover weekly
R4 | 2 | 2 | Audit labels
R5 | 3 | 5 | Test backup power before gate
Positions: R1 (L4, I3), R2 (L2, I5), R3 (L3, I4), R4 (L2, I2), R5 (L3, I5).

## Slide 8
Decision: fund $440k now; rollout only on a Week 10 GO
Go / no-go gate, thresholds, fallback and next step — Aster cold-chain (synthetic data)
FUNDING ASK
$440k for Resilient
$155k/yr saving · 2.8-yr payback · $25k 3-yr net
GO / NO-GO GATE — WEEK 10
All three thresholds must pass (AND):
NEXT ROLLOUT
Weeks 11–14, only after Gate GO
Threshold 1: Uptime ≥ 99.5%
Threshold 2: All five sites ≥ 95% on time
Threshold 3: Backup-power test passed
GO — all thresholds pass → proceed to rollout, Weeks 11–14
HOLD — if ANY threshold fails: stop, remediate, re-gate. No rollout.