## Slide 1
ASTER COLD-CHAIN / OPERATIONS COMMITTEE
Choose Resilient: uptime now outranks price
Invest $440k in regional distribution capacity. Require proof at the week-10 gate before rollout in weeks 11–14.
$440k
Investment
$155k
Annual saving
2.8 years
Simple payback
$25k
Three-year net saving
99.8% reference uptime clears the 99.5% threshold
Measured uptime, all five sites’ on-time performance and the backup-power test must still pass. HOLD rollout if any threshold fails.
All data synthetic • Currency $k • Payback = investment ÷ annual saving • Three-year net = 3 × saving − investment
1 / 8

## Slide 2
M4 beats target; the six-month shortfall is still 520
Six-month throughput • shipments • actual remains below target in five of six months
Chart: 
| M1 | M2 | M3 | M4 | M5 | M6
Actual | 870 | 850 | 720 | 1080 | 720 | 910
Target | 950 | 970 | 840 | 1040 | 820 | 1050
TOTAL ACTUAL
5,150
TOTAL TARGET
5,670
SHORTFALL
520
shipments
Synthetic data • Shortfall = total target − total actual • Monthly totals are separate from daily site demand and capacity.
2 / 8

## Slide 3
Resilient is the only option above the uptime gate
Reference options • all prices, savings, uptime assumptions and lead times remain unchanged
Option | Investment $k | Saving $k/yr | Uptime % | Lead weeks
Lean | 220 | 95 | 97.5 | 6
Balanced | 350 | 130 | 99.0 | 8
Resilient | 440 | 155 | 99.8 | 10
Selected: Resilient
Versus Balanced: $90k more investment, $25k more annual saving and 2 more lead weeks.
Uptime takes priority over price
99.8% reference uptime is 0.3 percentage points above the gate. Measured proof is still required.
Synthetic data • Currency $k • Lead weeks are option references • Rollout requires a GO decision at the week-10 gate.
3 / 8

## Slide 4
A 20% savings downside turns the three-year net negative
Resilient sensitivity • fixed investment of $440k • annual saving in $k
Chart: 
| Downside 80% | Base 100% | Upside 120%
Annual saving $k | 124 | 155 | 186
Returns at each savings level
Scenario | Payback years | 3-year net $k
Downside | 3.5 | −68
Base | 2.8 | 25
Upside | 2.4 | 118
Base net saving is only $25k over three years; downside falls to −$68k.
Synthetic data • Payback = 440 ÷ annual saving, rounded to 1 decimal • Three-year net = 3 × annual saving − 440
4 / 8

## Slide 5
South is capacity-constrained despite network headroom
Daily site demand and capacity • current on-time performance and accountable owners
Site | Demand/day | Capacity/day | On time % | Owner
North | 340 | 380 | 95 | Ari
Central | 290 | 330 | 94 | Bo
South | 340 | 320 | 89 | Cy
East | 320 | 340 | 94 | Dee
West | 310 | 340 | 96 | Eli
Demand: 1,600/day
Capacity: 1,710/day
Headroom: 110/day
South has a 20/day deficit. Central, South and East are below the ≥95% on-time gate.
Synthetic data • Capacity-constrained means demand exceeds capacity • Daily figures are separate from six-month shipment totals.
5 / 8

## Slide 6
Validation and training both feed the week-10 gate
Connected delivery roadmap • dependencies flow left to right • weeks from approval
Technical
People
Design
Weeks 1–2
Build
Weeks 3–5
Validate
Weeks 6–8
Train
Weeks 6–8
Decision gate
Week 10
Rollout
Weeks 11–14
Design starts independently. Build enables Validate and Train. Both must finish before the gate; only GO enables rollout.
Synthetic plan • Activity weeks unchanged through validation and training • Gate GO requires every threshold on slide 8.
6 / 8

## Slide 7
R1 is most likely; R2 and R5 share the highest impact
Five risks • stated likelihood and impact scores on a 1–5 scale • mitigation for every risk
Impact ↑ (1–5)
Likelihood → (1–5)
Impact | 1 | 2 | 3 | 4 | 5
5 |  | R2 | R5 |  | 
4 |  |  | R3 |  | 
3 |  |  |  | R1 | 
2 |  | R4 |  |  | 
1 |  |  |  |  | 
Mitigations • R5 tests gate readiness
Risk ID | Mitigation
R1 | Cross-train two crews
R2 | Dual-source hardware
R3 | Test failover weekly
R4 | Audit labels
R5 | Test backup power before gate
Synthetic risk assessment • Likelihood increases to the right; impact increases upward • IDs mark the scored coordinates.
7 / 8

## Slide 8
Approve $440k for Resilient; gate rollout at week 10
Fund the selected investment now. Authorize rollout in weeks 11–14 only when every gate condition passes.
WEEK 10 / ALL THREE CONDITIONS REQUIRED
1 Uptime ≥99.5%
2 All five sites ≥95% on time
3 Backup-power test passed
GO: every threshold passes
Proceed to rollout
Weeks 11–14
HOLD: any threshold fails
Hold rollout, remediate and revalidate before a new GO decision.
Site gaps remain: Central 94%, South 89%, East 94% on time. Resilient’s 99.8% uptime is a reference; verify it and backup power.
Synthetic decision case • Investment $440k • Annual saving $155k • Payback 2.8 years • Three-year net saving $25k
8 / 8