## Slide 1
Recommendation: fund Resilient — $440k returns $155k a year, pays back in 2.8 years and clears the uptime gate
$440k
Investment (one-time)
$155k
Annual saving
2.8 yrs
Simple payback (440 ÷ 155)
+$25k
Three-year net (3 × 155 − 440)
Why Resilient: uptime now outranks price
• Only option rated above the 99.5% uptime gate threshold (99.8%)
• Output trails target in five of six months: 5,630 vs 5,960 readings (−330)
• Costs $90k more than Balanced with a 10-week lead; three-year net +$25k vs +$40k
• Thin margin: three-year net turns −$68k in the 80% downside
DECISION REQUESTED
Approve $440k for Resilient now.
GO to rollout (weeks 11–14) at the week-10 gate only if uptime ≥99.5%, all five sites ≥95% on time and the backup-power test passes; otherwise HOLD.
Cedar sensor network · field sensor rollout · engineering steering group · synthetic data · 1/8

## Slide 2
Output missed target in five of six months: 5,630 vs 5,960 readings, a 330-reading gap
Monthly sensor readings, actual vs target, M1–M6 (M4 actual corrected to 1,150)
Chart: 
| M1 | M2 | M3 | M4 | M5 | M6
Actual | 890 | 890 | 940 | 1150 | 860 | 900
Target | 970 | 980 | 1070 | 1040 | 930 | 970
5,630
Total actual readings, M1–M6
5,960
Total target readings, M1–M6
−330
Gap: 5.5% below target. Only M4 beat target (+110); largest miss M3 (−130).
Cedar sensor network · field sensor rollout · synthetic data · 2/8

## Slide 3
Resilient is the only option rated above the 99.5% uptime gate; it costs $90k more than Balanced
Reference option values unchanged · payback = investment ÷ saving · 3-yr net = 3 × saving − investment
Option | Investment $k | Saving $k/yr | Uptime % | Lead weeks | Payback yrs | 3-yr net $k
Lean | 210 | 95 | 97.5 | 6 | 2.2 | +75
Balanced | 350 | 130 | 99.0 | 8 | 2.7 | +40
Resilient (selected) | 440 | 155 | 99.8 | 10 | 2.8 | +25
vs Lean
+$230k buys +$60k/yr saving and +2.3 pts uptime; lead time is 4 weeks longer and 3-yr net falls $75k → $25k.
vs Balanced
+$90k buys +$25k/yr saving and +0.8 pt uptime; lead time 8 → 10 weeks, payback 2.7 → 2.8 yrs, 3-yr net $40k → $25k.
Tradeoff accepted
Lowest 3-yr net (+$25k) and longest lead time, in exchange for the only rated uptime (99.8%) that clears the 99.5% gate.
Cedar sensor network · field sensor rollout · synthetic data · 3/8

## Slide 4
Payback ranges 2.4–3.5 years; the three-year net stays positive only at ≥95% of base saving
Annual saving by scenario, $k/yr (80 / 100 / 120% of Resilient $155k) · investment fixed at $440k
Chart: 
| Downside 80% | Base 100% | Upside 120%
Annual saving $k | 124 | 155 | 186
Scenario | Saving $k/yr | Payback yrs | 3-yr net $k
Downside 80% | 124 | 3.5 | −68
Base 100% | 155 | 2.8 | +25
Upside 120% | 186 | 2.4 | +118
Three-year break-even
Needs ≥ $147k/yr (≈95% of base) to recover $440k in three years. Base clears it by $8k/yr; the downside falls short by $23k/yr.
Cedar sensor network · field sensor rollout · synthetic data · 4/8

## Slide 5
Daily demand of 1,700 exceeds capacity of 1,660; North, Central and West are capacity-constrained
Readings per day by site (daily rates, not six-month totals) · gap = capacity − demand
Site | Demand/day | Capacity/day | On time % | Owner | Gap/day | Status
North | 400 | 360 | 91 | Ari | −40 | Constrained
Central | 400 | 320 | 96 | Bo | −80 | Constrained
South | 260 | 320 | 97 | Cy | +60 | Spare
East | 290 | 360 | 89 | Dee | +70 | Spare
West | 350 | 300 | 92 | Eli | −50 | Constrained
Total | 1,700 | 1,660 | — | — | −40 | Short
Capacity-constrained
North −40/day
Central −80/day
West −50/day
South and East have spare.
Gate exposure
Only Central (96%) and South (97%) meet ≥95% on time; North, East and West must improve by the week-10 gate.
Cedar sensor network · field sensor rollout · synthetic data · 5/8

## Slide 6
Rollout moves to weeks 11–14 and starts only after Validate and Train both clear the week-10 gate
Wk 1–2
Wk 3–5
Wk 6–8
Wk 10
Wk 11–14
Technical
People
Design
Wk 1–2
Build · Wk 3–5
after Design
Validate · Wk 6–8
after Build
Train · Wk 6–8
after Build
GATE
GO
/
HOLD
Rollout · Wk 11–14
after Gate GO
Dependencies: Design → Build → Validate; Build → Train; Validate AND Train → Gate (week 10); Gate GO → Rollout (weeks 11–14). Other activity weeks unchanged. Any failed gate threshold = HOLD.
Cedar sensor network · field sensor rollout · synthetic data · 6/8

## Slide 7
New risk R5 (backup power) scores highest at 15; its mitigation must be done before the gate
5
4
3
2
1
1
2
3
4
5
Likelihood (1–5) →
Impact
(1–5)
↑
R1
R2
R3
R4
R5
ID | Likelihood × Impact = score | Mitigation
R1 | 4 × 3 = 12 | Cross-train two crews
R2 | 2 × 5 = 10 | Dual-source hardware
R3 | 3 × 4 = 12 | Test failover weekly
R4 | 2 × 2 = 4 | Audit labels
R5 | 3 × 5 = 15 | Test backup power before gate

## Slide 8
Decision: approve $440k for Resilient now; release rollout at week 10 only if all three thresholds pass
NOW
Approve $440k · Resilient
WEEK 10 · GATE
Go / no-go review
WEEKS 11–14
Rollout if GO
Gate threshold (all must pass) | Required | Status today
Uptime | ≥ 99.5% | Resilient rated 99.8%; confirm in Validate
On-time delivery | All five sites ≥ 95% | 2 of 5 meet (Central, South)
Backup-power test | Passed | Test before gate (R5)
HOLD if any threshold fails
Rollout does not start in week 11; return to this group with the failed threshold and a fix plan.
GO (all three pass) → rollout weeks 11–14. Case: payback 2.8 yrs, three-year net +$25k (−$68k at 80% downside, +$118k at 120% upside).
Cedar sensor network · field sensor rollout · synthetic data · 8/8