## Slide 1
Recommendation: fund Balanced - $350k for $130k/yr saving
Aster cold-chain | Regional distribution capacity | Operations committee decision | All data synthetic
CHOSEN INVESTMENT
$350k
Balanced option
ANNUAL SAVING
$130k/yr
Base case
SIMPLE PAYBACK
2.7 years
350 / 130
THREE-YEAR NET SAVING
$40k
3 x 130 - 350
Why Balanced
- 99.0% uptime and 8-week lead time
- $35k/yr more saving than Lean, for $130k more investment
- $90k less upfront than Resilient, accepting $25k/yr less saving
- Protects value with a Week 8 go / no-go gate before rollout
DECISION ASKED TODAY
Approve $350k for Balanced.
Rollout in Weeks 9-12 only if the Week 8 gate returns GO.
Currency: $k | Payback = investment / annual saving | Three-year net = 3 x saving - investment

## Slide 2
Six months fell 690 shipments short: 4,980 actual vs 5,670 target
Shipments by month, M1-M6 - actual vs target (shipments)
Chart: 
| M1 | M2 | M3 | M4 | M5 | M6
Actual | 870 | 850 | 720 | 910 | 720 | 910
Target | 950 | 970 | 840 | 1040 | 820 | 1050
TOTAL ACTUAL
4,980 shipments
TOTAL TARGET
5,670 shipments
GAP
690 shipments
12.2% below target
Actual was below target in every month M1-M6. Gap = 5,670 - 4,980 = 690 shipments.
Aster cold-chain | Six-month performance | Units: shipments

## Slide 3
Balanced is the middle path: near-top uptime without the $440k Resilient price
All option prices shown unchanged. Selected option: Balanced.
Option | Investment $k | Saving $k/yr | Uptime % | Lead weeks
Lean | 220 | 95 | 97.5 | 6
Balanced | 350 | 130 | 99.0 | 8
Resilient | 440 | 155 | 99.8 | 10
Selected-option tradeoff - Balanced ($350k, $130k/yr, 99.0%, 8 weeks)
Vs Lean: pay $130k more and wait 2 weeks longer, gain $35k/yr saving and +1.5 points uptime.
Vs Resilient: spend $90k less and deliver 2 weeks sooner, give up $25k/yr saving and 0.8 points uptime.
Reference prices remain Lean $220k and Resilient $440k after the Balanced recommendation.

## Slide 4
Downside still pays back in 3.4 years; base case nets $40k over three years
Annual saving by scenario ($k/yr) - Balanced, $350k investment
Chart: 
| Downside 80% | Base 100% | Upside 120%
Annual saving $k/yr | 104 | 130 | 156
Payback and three-year net by scenario
Scenario | Saving $k/yr | Payback yrs | 3-year net $k
Downside 80% | 104 | 3.4 | -38
Base 100% | 130 | 2.7 | 40
Upside 120% | 156 | 2.2 | 118
Downside is -$38k at Year 3: the Week 8 gate must protect against committing rollout on weak evidence.
Scenarios = 80% / 100% / 120% of $130k/yr. Payback = 350 / saving. Three-year net = 3 x saving - 350.
Aster cold-chain | Balanced scenarios | Currency: $k

## Slide 5
South is the only capacity-constrained site: 340/day demand vs 320/day capacity
Daily demand and capacity by site (shipments/day) - not six-month totals
Site | Demand/day | Capacity/day | On time % | Owner
North | 340 | 380 | 95 | Ari
Central | 290 | 330 | 94 | Bo
South | 340 | 320 | 89 | Cy
East | 320 | 340 | 94 | Dee
West | 310 | 340 | 96 | Eli
TOTAL DAILY DEMAND
1,600 / day
TOTAL DAILY CAPACITY
1,710 / day
CONSTRAINED: South only
20/day over capacity; 89% on time
Network headroom is 110/day overall (1,710 - 1,600), but it sits at North, Central, East and West - not South.

## Slide 6
Roadmap: Week 8 Decision gate after Validate + Train, then rollout Weeks 9-12
Technical
People
Design
Weeks 1-2
Dep: None
Build
Weeks 3-5
Dep: Design
Validate
Weeks 6-8
Dep: Build
Train
Weeks 6-8
Dep: Build
DECISION GATE
Week 8
Dep: Validate + Train
Rollout
Weeks 9-12
Dep: Gate GO
Sequence: Design (1-2) -> Build (3-5) -> Validate (6-8) and Train (6-8) -> Decision Gate (Week 8) -> Rollout (9-12, Gate GO only).
Arrows show dependencies. No rollout activity starts before a GO decision at the Week 8 gate.

## Slide 7
Top risks cluster at high impact: R2 and R3 need active mitigation
R1
R2
R3
R4
Likelihood 1-5 (1 at bottom, 5 at top)
Impact 1-5 ->
1
2
3
4
5
5
4
3
2
1
ID | Likelihood 1-5 | Impact 1-5 | Mitigation
R1 | 4 | 3 | Cross-train two crews
R2 | 2 | 5 | Dual-source hardware
R3 | 3 | 4 | Test failover weekly
R4 | 2 | 2 | Audit labels
Read: R1 = L4 x I3, R2 = L2 x I5, R3 = L3 x I4, R4 = L2 x I2. Matrix plots Likelihood (vertical) by Impact (horizontal).

## Slide 8
Decision: fund Balanced now; Week 8 gate is GO only if every threshold passes
FUNDING - BALANCED
Investment: $350k
Annual saving: $130k/yr
Payback: 2.7 years
Three-year net: $40k
GO / NO-GO GATE - WEEK 8
1. Uptime >= 99.5%
2. All five sites >= 95% on time
3. Backup-power test passed
All three must pass (AND).
IF GO
Rollout Weeks 9-12
IF ANY FAILS
HOLD - no rollout
Fallback and next step: HOLD if any threshold fails at Week 8 - fix and re-test before any rollout. On GO, proceed directly to rollout in Weeks 9-12 (Gate dependency: Validate AND Train complete).
Gate rule: Uptime >=99.5% AND all five sites >=95% on time AND backup-power test passed.
Aster cold-chain | Balanced $350k | Currency: $k | All data synthetic