## Slide 1
Recommend Balanced: $350k buys $130k/yr in savings with a
2.7-year payback
Aster cold-chain · regional distribution capacity · operations committee decision
$350k
Investment (Balanced option)
$130k/yr
Annual saving
2.7 yrs
Simple payback (350 ÷ 130)
$40k
Three-year net (3 × 130 − 350)
Why act now
• Shipments ran 690 below target over six months (4,980 vs 5,670)
• South's demand (340/day) already exceeds its capacity (320/day)
• Balanced costs $90k less than Resilient and saves $35k/yr more than Lean
DECISION REQUESTED
Fund $350k for Balanced now; release the week 9–12 rollout only on a GO at the week-8 gate.
Gate: uptime ≥99.5%, all five sites ≥95% on time, backup-power test passed. Any miss → HOLD.

## Slide 2
Shipments ran 690 below target over six months: 4,980 actual
vs 5,670
Monthly shipments, actual vs target, M1–M6
Shipments per month
Chart: 
| M1 | M2 | M3 | M4 | M5 | M6
Actual | 870 | 850 | 720 | 910 | 720 | 910
Target | 950 | 970 | 840 | 1040 | 820 | 1050
4,980
Total actual shipments
5,670
Total target shipments
−690
Gap (12.2% below target)
Every month missed target; monthly shortfall ranged from 80 (M1) to 140 (M6).

## Slide 3
Balanced gives up Resilient's 99.8% uptime to cost $90k less
and land 2 weeks sooner
Reference prices unchanged · payback = investment ÷ annual saving · 3-yr net = 3 × saving − investment
Option | Investment $k | Saving $k/yr | Uptime % | Lead weeks | Payback yrs | 3-yr net $k
Lean | 220 | 95 | 97.5 | 6 | 2.3 | 65
Balanced (selected) | 350 | 130 | 99.0 | 8 | 2.7 | 40
Resilient | 440 | 155 | 99.8 | 10 | 2.8 | 25
Why not Lean
Best payback (2.3 yrs) and net ($65k), but 97.5% uptime is 2 points short of the 99.5% gate.
Why Balanced
$130k/yr saving and an 8-week lead fit the week-8 gate; $40k three-year net.
Tradeoff we accept
Rated 99.0% uptime is below the 99.5% gate: the pilot must prove +0.5 pt, or we HOLD.

## Slide 4
Base case nets $40k over three years; an 80% downside loses
$38k
Annual saving at 80/100/120% of Balanced's $130k; investment fixed at $350k
Annual saving, $k
Chart: 
| Downside 80% | Base 100% | Upside 120%
Annual saving $k | 104 | 130 | 156
Scenario | Saving $k/yr | Payback yrs | 3-yr net $k
Downside 80% | 104 | 3.4 | −38
Base 100% | 130 | 2.7 | 40
Upside 120% | 156 | 2.2 | 118
Breakeven within three years needs about $117k/yr saving (≈90% of base). Below that, the investment does not pay back in three years.

## Slide 5
South is the only capacity-constrained site: 340/day demand vs
320 capacity
Daily demand and capacity by site; three sites are also below the 95% on-time gate
Site | Demand/day | Capacity/day | Headroom/day | On time % | Owner
North | 340 | 380 | +40 | 95 | Ari
Central | 290 | 330 | +40 | 94 | Bo
South | 340 | 320 | −20 | 89 | Cy
East | 320 | 340 | +20 | 94 | Dee
West | 310 | 340 | +30 | 96 | Eli
Total | 1,600 | 1,710 | +110 | — | —
Below 95% on time: Central 94%, South 89%, East 94%. All must reach 95% by the week-8 gate.
1,600
Total demand per day
1,710
Total capacity per day
CAPACITY-CONSTRAINED
South: short 20/day (340 demand vs 320 capacity)

## Slide 6
Rollout begins week 9 only after Validate and Train both clear
the week-8 gate
12-week plan in two lanes; connectors show dependencies
Week 1
Week 8 gate
Week 12
Technical
Decision
People
Design wk 1–2
Build wk 3–5
Validate wk 6–8
Rollout wk 9–12 (needs GO)
Train wk 6–8
GATE
wk 8
Dependencies: Design → Build → Validate; Build → Train; Validate AND Train → Gate (wk 8); Gate GO → Rollout (wk 9–12). No GO = HOLD.

## Slide 7
Two risks score highest (12 of 25): crew coverage R1 and
failover R3
Likelihood × impact on 1–5 scales; each ID sits at its rated coordinates
Likelihood (1 = low, 5 = high) →
Impact (1–5) ↓
I \ L | 1 | 2 | 3 | 4 | 5
5 |  | R2 |  |  | 
4 |  |  | R3 |  | 
3 |  |  |  | R1 | 
2 |  | R4 |  |  | 
1 |  |  |  |  | 
ID | L × I | Mitigation
R1 | 4 × 3 = 12 | Cross-train two crews
R2 | 2 × 5 = 10 | Dual-source hardware
R3 | 3 × 4 = 12 | Test failover weekly
R4 | 2 × 2 = 4 | Audit labels
Act first on R1 and R3; R2 is unlikely but carries maximum impact.

## Slide 8
Decision: fund $350k now; GO to the week 9–12 rollout only if
all three gate tests pass
Go/no-go at week 8; any failed threshold triggers HOLD
Fund $350k
Build & train wk 1–8
Gate wk 8
GO: rollout wk 9–12
Gate threshold | Required for GO | Current gap
Uptime | ≥ 99.5% | Balanced rated 99.0%
On time, all five sites | ≥ 95% each | Central 94, South 89, East 94
Backup-power test | Passed | Must pass at gate
IF ANY THRESHOLD FAILS → HOLD
Rollout does not start. Close the failing gap, then re-run the gate.
Ask today: approve $350k for Balanced ($130k/yr saving, 2.7-yr payback, $40k three-year net) and these week-8 gate criteria.