## Slide 1
Recommend Balanced: $350k saves $130k a year and pays
back in 2.7 years
Cedar sensor network · field sensor rollout · engineering steering group · synthetic data
$350k
Investment (Balanced option)
$130k
Annual saving
2.7 yrs
Simple payback ($350k ÷ $130k)
+$40k
Three-year net (3 × 130 − 350)
Why Balanced
$90k less than Resilient with a higher 3-yr net ($40k vs $25k); 99.0% design uptime vs 97.5% for Lean.
What we must fix
Readings ran 500 (8.4%) below target over six months; North, Central and West exceed daily capacity.
How we stay safe
Week 8 gate: uptime ≥99.5%, all five sites ≥95% on time, backup-power test passed. Any miss = HOLD.
Decision requested: approve $350k now; rollout (Weeks 9–12) proceeds only on a Week 8 GO.

## Slide 2
Readings trailed target in all six months, leaving a 500-reading
gap
Monthly sensor readings, actual vs target, M1–M6
Readings per month
Chart: 
| M1 | M2 | M3 | M4 | M5 | M6
Actual | 890 | 890 | 940 | 980 | 860 | 900
Target | 970 | 980 | 1070 | 1040 | 930 | 970
5,460
Total actual readings
5,960
Total target readings
−500
Gap: 8.4% below target

## Slide 3
Balanced gives up the fastest payback to gain uptime at $90k
below Resilient
Reference option prices unchanged; payback = investment ÷ saving; 3-yr net = 3 × saving − investment
Option | Investment $k | Saving $k/yr | Uptime % | Lead weeks | Payback yrs | 3-yr net $k
Lean | 210 | 95 | 97.5 | 6 | 2.2 | 75
Balanced (selected) | 350 | 130 | 99.0 | 8 | 2.7 | 40
Resilient | 440 | 155 | 99.8 | 10 | 2.8 | 25
Versus Lean
+$140k and slower payback (2.7 vs 2.2 yrs) buys +1.5 pts uptime (99.0% vs 97.5%).
Versus Resilient
$90k less capital, higher 3-yr net ($40k vs $25k), 2 weeks faster; gives up 0.8 pts uptime.
Tradeoff to watch
99.0% design uptime is below the 99.5% gate; measured uptime must beat design or we HOLD.

## Slide 4
Balanced stays net-positive unless savings fall 20%; downside
3-yr net is −$38k
Scenarios at 80% / 100% / 120% of the $130k selected annual saving; investment fixed at $350k
Annual saving, $k per year
Chart: 
| Downside 80% | Base 100% | Upside 120%
Annual saving $k | 104 | 130 | 156
Scenario | Saving $k/yr | Payback yrs | 3-yr net $k
Downside 80% | 104 | 3.4 | −38
Base 100% | 130 | 2.7 | 40
Upside 120% | 156 | 2.2 | 118
Base and upside recover the $350k inside three years. At downside the payback (3.4 yrs) runs past the three-year horizon.
Payback = $350k ÷ annual saving (one decimal). Three-year net = 3 × annual saving − $350k.

## Slide 5
North, Central and West exceed daily capacity; network is short
40 readings/day
Daily demand and capacity by site (readings/day, not six-month totals)
Site | Demand/day | Capacity/day | Capacity − demand | On time % | Owner
North | 400 | 360 | −40 | 91 | Ari
Central | 400 | 320 | −80 | 96 | Bo
South | 260 | 320 | +60 | 97 | Cy
East | 290 | 360 | +70 | 89 | Dee
West | 350 | 300 | −50 | 92 | Eli
Total | 1,700 | 1,660 | −40 |  | 
1,700
Total demand, readings/day
1,660
Total capacity, readings/day
Capacity-constrained: North (−40), Central (−80), West (−50)
Gate check: only Central (96%) and South (97%) meet the 95% on-time threshold today; North, East and West must improve by Week 8.

## Slide 6
Build and training converge on the Week 8 gate before a 4-week
rollout
Weeks 1–12 · lines show dependencies · gate needs Validate AND Train
Technical
Decision
People
Design
Wk 1–2
Build
Wk 3–5
Validate
Wk 6–8
Rollout
Wk 9–12 (after GO)
Gate
Wk 8
Train
Wk 6–8
Dependencies: Design → Build → Validate · Build → Train · Validate AND Train → Gate (Week 8) · Gate GO → Rollout (Weeks 9–12)

## Slide 7
R1 and R3 carry the highest exposure (L × I = 12); each risk has
a named mitigation
5
4
3
2
1
1
2
3
4
5
Likelihood (1–5) →
↑ Impact (1–5)
R1
R2
R3
R4
ID | Likelihood | Impact | L × I | Mitigation
R1 | 4 | 3 | 12 | Cross-train two crews
R2 | 2 | 5 | 10 | Dual-source hardware
R3 | 3 | 4 | 12 | Test failover weekly
R4 | 2 | 2 | 4 | Audit labels

## Slide 8
Approve $350k for Balanced now; release rollout only on a
Week 8 GO
Gate at Week 8 requires all three thresholds; any single failure means HOLD
Approve $350k today
Build & train Wk 1–8
Gate: Week 8
GO → Rollout Wk 9–12
Uptime ≥ 99.5%
Balanced design is 99.0%; measured uptime must beat it
All 5 sites ≥ 95% on time
Today 2 of 5 pass (Central 96%, South 97%)
Backup-power test passed
Pass/fail result required at the Week 8 gate
GO (all three pass): start rollout in Weeks 9–12; base case pays back in 2.7 years, +$40k over three years
HOLD (any threshold fails): no rollout; fix the failing threshold, re-test and return to this committee