## Slide 1
Recommend Resilient Cedar sensor network
Fictional decision committee • Engineering steering group • All data synthetic • Currency $k
$440k
Chosen investment — Resilient
$155k/yr
Annual saving
2.8 years
Simple payback: 440 / 155
$25k
Three-year net: 3×155 − 440
DECISION ASKED: Approve Resilient now, conditional on the Week-10 gate.
Resilient delivers 99.8% uptime in 10 weeks — the highest uptime, now prioritised over price.
Why now
Six-month actual trails target by 330 readings. Delay keeps the gap open.
Why Resilient
Top uptime at 99.8%, 10-week lead. Payback 2.8 years at base saving.
Protection
Week-10 GO only if every threshold passes. Any failure = HOLD. Rollout Weeks 11–14.

## Slide 2
Six-month actual trails target by 330 readings
Readings by month, M1–M6 • All 12 monthly values labelled
Readings per month — Actual vs Target
Chart: 
| M1 | M2 | M3 | M4 | M5 | M6
Actual | 890 | 890 | 940 | 1150 | 860 | 900
Target | 970 | 980 | 1070 | 1040 | 930 | 970
5,630
Total actual readings (M1–M6)
5,960
Total target readings (M1–M6)
−330
Gap: actual − target = −330 readings
Five months are below target; M4 is above target (+110). The largest shortfalls are M3 (−130) and M2 (−90).

## Slide 3
Resilient buys the highest uptime at the highest price
Reference option prices unchanged • Investment and saving in $k
Option | Investment $k | Saving $k/yr | Uptime % | Lead weeks
Lean | 210 | 95 | 97.5 | 6
Balanced | 350 | 130 | 99.0 | 8
Resilient | 440 | 155 | 99.8 | 10
Selected: Resilient — $440k • $155k/yr • Payback 2.8 years • 3-yr net $25k
Versus Balanced (+$90k)
Pays $90k more and takes 2 weeks longer, for +$25k/yr saving and +0.8 points of uptime (99.8% vs 99.0%).
Versus Lean (+$230k)
Pays $230k more and takes 4 weeks longer, for +$60k/yr saving and +2.3 points of uptime (99.8% vs 97.5%).
Tradeoff in one line: with uptime now outranking price, Resilient is the choice — the committee pays the top price and accepts the longest lead for maximum reliability.

## Slide 4
Base case pays back in 2.8 years; downside does not
Resilient investment fixed at $440k • Scenarios at 80% / 100% / 120% of $155k/yr saving
Annual saving by scenario ($k/yr)
Chart: 
| Downside 80% | Base 100% | Upside 120%
Annual saving $k/yr | 124 | 155 | 186
Scenario | Saving $k/yr | Payback yrs | 3-yr net $k
Downside 80% | 124 | 3.5 | −68
Base 100% | 155 | 2.8 | 25
Upside 120% | 186 | 2.4 | 118
Formulas: Payback = 440 / saving. Three-year net = 3 × saving − 440.
Read this honestly: at 80% saving the three-year net is −$68k. Approval relies on validating the base saving before rollout — hence the Week-10 gate.

## Slide 5
Three of five sites are capacity-constrained today
Daily demand and capacity by site — not six-month totals
Site | Demand/day | Capacity/day | On time % | Owner
North | 400 | 360 | 91 | Ari
Central | 400 | 320 | 96 | Bo
South | 260 | 320 | 97 | Cy
East | 290 | 360 | 89 | Dee
West | 350 | 300 | 92 | Eli
1,700/day
Total daily demand (all five sites)
1,660/day
Total daily capacity — shortfall 40/day
Capacity-constrained
(demand > capacity)
• North 400 > 360
• Central 400 > 320
• West 350 > 300
Not constrained: South (260 < 320) and East (290 < 360).
On-time is a separate problem: North 91%, East 89% and West 92% all sit below the 95% gate threshold.

## Slide 6
Build feeds both validation and training before the gate
Two-lane roadmap, Weeks 1–14 • Every activity, week range and dependency shown
Technical
People
Design
Weeks 1–2
Dep: None
Build
Weeks 3–5
Dep: Design
Validate
Weeks 6–8
Dep: Build
Train
Weeks 6–8
Dep: Build
DECISION GATE
Week 10
Dep: Validate AND Train
Rollout
Weeks 11–14
Dep: Gate GO
Critical chain: Design → Build → Validate → Decision Gate (Week 10) → Rollout (Weeks 11–14). Training runs Weeks 6–8 in parallel with validation and must also finish before the gate.

## Slide 7
R5 is now the highest-scored risk before the gate
Likelihood × Impact, each scored 1–5 • Risk IDs plotted at their scored coordinates
Impact →
5
4
3
2
1
1 2 3 4 5
Likelihood → (1 low to 5 high)
R1
R2
R3
R4
R5
ID | Likelihood 1-5 | Impact 1-5 | Mitigation
R1 | 4 | 3 | Cross-train two crews
R2 | 2 | 5 | Dual-source hardware
R3 | 3 | 4 | Test failover weekly
R4 | 2 | 2 | Audit labels
R5 | 3 | 5 | Test backup power before gate
Watch first: R5 (3 × 5) and R2 (Impact 5), then R3 (3 × 4) and R1 (4 × 3). R4 (2 × 2) is monitor-only.

## Slide 8
Fund $440k now; GO only if every gate threshold passes
Decision gate at Week 10 • Fallback is HOLD — no partial GO
$440k
Funding requested — Resilient
$155k/yr
Base saving • Payback 2.8 yrs
Week 10
Decision gate timing
Weeks 11–14
Next rollout if GO
GO requires ALL three thresholds:
1. Uptime ≥ 99.5%
2. All five sites ≥ 95% on time
3. Backup-power test passed
GO
All thresholds pass
→ Rollout
Weeks 11–14
HOLD
Any threshold fails
→ No rollout
Fix, then re-gate
Decision asked today: approve $440k for Resilient and the Week-10 gate rule above. Funding does not authorise rollout — only a full GO at Week 10 does.