## Slide 1
CEDAR SENSOR NETWORK / ENGINEERING STEERING GROUP
Choose Resilient: uptime now takes priority over price
Approve the $440k field sensor investment. Release deployment only after the week-10 readiness gate.
$440k
Investment · Resilient
$155k
Annual saving · base
2.8 years
Simple payback
$25k
Three-year net saving
99.8% reference uptime supports the choice; measured readiness still governs GO
Resilient exceeds the 99.5% uptime threshold on reference performance. All five sites and backup power must also pass.
Synthetic decision case · Currency: $k · Payback = investment / annual saving · Three-year net = 3 × saving − investment
01 / 08

## Slide 2
Readings finish 330 below target despite M4 recovery
Six-month actual is 94.5% of target. M4 exceeds plan by 110 readings; the other five months remain below target.
Readings per month
Chart: 
| M1 | M2 | M3 | M4 | M5 | M6
Actual | 890 | 890 | 940 | 1150 | 860 | 900
Target | 970 | 980 | 1070 | 1040 | 930 | 970
5,630
Total actual readings
5,960
Total target readings
330
Shortfall
Target − actual
Synthetic data · M4 actual corrected to 1,150 readings · Site demand and capacity are separate daily measures.
02 / 08

## Slide 3
Resilient is the only reference option above the uptime gate
Uptime outranks price. All reference investments, annual savings, uptime figures and lead times remain unchanged.
Option | Investment $k | Saving $k/yr | Uptime % | Lead weeks
Lean | 210 | 95 | 97.5 | 6
Balanced | 350 | 130 | 99.0 | 8
Resilient | 440 | 155 | 99.8 | 10
SELECTED: RESILIENT
99.8% reference uptime is 0.3 percentage points above the 99.5% gate. Measured performance must still pass.
TRADEOFF VERSUS BALANCED
Pay $90k more for $25k more annual saving and 0.8 uptime points. Lead time increases by 2 weeks.
Synthetic reference options · Resilient three-year net: $25k versus Balanced $40k; the $15k reduction buys higher reference uptime.
03 / 08

## Slide 4
A 20% saving downside produces a $68k three-year net loss
Resilient sensitivity uses 80%, 100% and 120% of $155k annual saving; investment stays fixed at $440k.
Annual saving ($k/year)
Chart: 
| Downside 80% | Base 100% | Upside 120%
Annual saving | 124 | 155 | 186
Scenario | Payback years | 3-year net $k
Downside | 3.5 | −68
Base | 2.8 | 25
Upside | 2.4 | 118
The base case yields $25k net over three years. Downside payback extends to 3.5 years.
Synthetic sensitivity · Payback = 440 / annual saving, rounded to 1 decimal year · Three-year net = 3 × annual saving − 440
04 / 08

## Slide 5
North, Central and West are capacity-constrained
Daily demand exceeds total capacity by 40 readings. North, East and West also fall below the on-time gate.
Site | Demand/day | Capacity/day | On time % | Owner
North | 400 | 360 | 91 | Ari
Central | 400 | 320 | 96 | Bo
South | 260 | 320 | 97 | Cy
East | 290 | 360 | 89 | Dee
West | 350 | 300 | 92 | Eli
Total | 1,700 | 1,660 | — | —
Daily deficits: North 40 · Central 80 · West 50
Gate: all five sites must reach ≥95% on time
Synthetic site data · Demand and capacity are daily readings, not six-month totals · All site reference cells are unchanged.
05 / 08

## Slide 6
Gate moves to week 10; rollout follows in weeks 11–14
Design, Build, Validate and Train retain their original weeks. Both Validate and Train remain gate prerequisites.
Technical
People
Design
Weeks 1–2
Build
Weeks 3–5
Validate
Weeks 6–8
Train
Weeks 6–8
Decision
gate
Week 10
Rollout
Weeks 11–14
After Gate GO
Dependencies: Design has none → Build → Validate AND Train → Decision gate → Rollout on GO.
Synthetic delivery plan · Connections show prerequisites. 06 / 08

## Slide 7
R5 adds a second maximum-impact risk before the gate
R1 remains most likely. R2 and R5 each have impact 5; all five risks have explicit mitigations.
Likelihood ↑ (1 = low; 5 = high)
L / I | 1 | 2 | 3 | 4 | 5
5 |  |  |  |  | 
4 |  |  | R1 |  | 
3 |  |  |  | R3 | R5
2 |  | R4 |  |  | R2
1 |  |  |  |  | 
Impact → (1 = low; 5 = high)
Risk · L / I | Mitigation
R1 · 4 / 3 | Cross-train two crews
R2 · 2 / 5 | Dual-source hardware
R3 · 3 / 4 | Test failover weekly
R4 · 2 / 2 | Audit labels
R5 · 3 / 5 | Test backup power before gate
R5 mitigation supplies evidence for the backup-power gate.
Synthetic risk register · Matrix rows show likelihood; columns show impact · R1–R4 coordinates and mitigations are unchanged.
07 / 08

## Slide 8
Approve $440k for Resilient; gate deployment in week 10
Funding supports the selected option. GO requires completed Validate and Train plus every readiness threshold below.
FUNDING REQUEST
$440k
Resilient
Cedar sensor network
Base case
$155k annual saving
2.8-year payback
$25k three-year net
WEEK 10: GO ONLY IF ALL THREE PASS
1 Uptime ≥99.5%
2 All five sites ≥95% on time
3 Backup-power test passed
ALL PASS → GO
Proceed to the next rollout in weeks 11–14.
ANY FAIL → HOLD
Remediate and re-test; defer rollout until all pass.
Synthetic decision case · Resilient reference uptime is 99.8%; demonstrated readiness determines the week-10 decision.
08 / 08