## Slide 1
Recommend Resilient: $440k buys 99.8% design uptime and
pays back in 2.8 years
Cedar sensor network · field sensor rollout · engineering steering group · synthetic data
$440k
Investment (Resilient option)
$155k
Annual saving
2.8 yrs
Simple payback ($440k ÷ $155k)
+$25k
Three-year net (3 × 155 − 440)
Why Resilient
Uptime now outranks price: 99.8% design uptime is the only option above the 99.5% gate; +0.8 pts vs Balanced for $90k more.
What we must fix
Readings ran 330 (5.5%) below target over six months; North, Central and West exceed daily capacity.
How we stay safe
Week 10 gate: uptime ≥99.5%, all five sites ≥95% on time, backup-power test passed. Any miss = HOLD.
Decision requested: approve $440k now; rollout (Weeks 11–14) proceeds only on a Week 10 GO.

## Slide 2
Readings trailed target in five of six months, leaving a
330-reading gap
Monthly sensor readings, actual vs target, M1–M6 · M4 actual corrected to 1,150 (110 above target)
Readings per month
Chart: 
| M1 | M2 | M3 | M4 | M5 | M6
Actual | 890 | 890 | 940 | 1150 | 860 | 900
Target | 970 | 980 | 1070 | 1040 | 930 | 970
5,630
Total actual readings
5,960
Total target readings
−330
Gap: 5.5% below target

## Slide 3
Resilient costs $90k more than Balanced but is the only option
designed above the 99.5% gate
Reference option values unchanged; payback = investment ÷ saving; 3-yr net = 3 × saving − investment
Option | Investment $k | Saving $k/yr | Uptime % | Lead weeks | Payback yrs | 3-yr net $k
Lean | 210 | 95 | 97.5 | 6 | 2.2 | 75
Balanced | 350 | 130 | 99.0 | 8 | 2.7 | 40
Resilient (selected) | 440 | 155 | 99.8 | 10 | 2.8 | 25
Versus Balanced
+$90k and 2 more lead weeks buy +0.8 pts uptime (99.8% vs 99.0%); payback 2.8 vs 2.7 yrs.
Versus Lean
+$230k buys +2.3 pts uptime (99.8% vs 97.5%); payback 2.8 vs 2.2 yrs.
Tradeoff accepted
Lowest 3-yr net of the three ($25k vs $40k Balanced, $75k Lean) because uptime outranks price.

## Slide 4
Resilient pays back inside three years in base and upside;
downside 3-yr net is −$68k
Scenarios at 80% / 100% / 120% of the $155k selected annual saving; investment fixed at $440k
Annual saving, $k per year
Chart: 
| Downside 80% | Base 100% | Upside 120%
Annual saving $k | 124 | 155 | 186
Scenario | Saving $k/yr | Payback yrs | 3-yr net $k
Downside 80% | 124 | 3.5 | −68
Base 100% | 155 | 2.8 | 25
Upside 120% | 186 | 2.4 | 118
Base and upside recover the $440k inside three years. At downside the payback (3.5 yrs) runs past the horizon.
Three-year break-even needs about $147k/yr, roughly 95% of the base saving.
Payback = $440k ÷ annual saving (one decimal). Three-year net = 3 × annual saving − $440k.

## Slide 5
North, Central and West exceed daily capacity; network is short
40 readings/day
Daily demand and capacity by site (readings/day, not six-month totals)
Site | Demand/day | Capacity/day | Capacity − demand | On time % | Owner
North | 400 | 360 | −40 | 91 | Ari
Central | 400 | 320 | −80 | 96 | Bo
South | 260 | 320 | +60 | 97 | Cy
East | 290 | 360 | +70 | 89 | Dee
West | 350 | 300 | −50 | 92 | Eli
Total | 1,700 | 1,660 | −40 |  | 
1,700
Total demand, readings/day
1,660
Total capacity, readings/day
Capacity-constrained: North (−40), Central (−80), West (−50)
Gate check: only Central (96%) and South (97%) meet the 95% on-time threshold today; North, East and West must improve by Week 10.

## Slide 6
Build and training converge on the Week 10 gate before a
4-week rollout
Weeks 1–14 · boxes placed on a week scale · lines show dependencies · gate needs Validate AND Train
Technical
Decision
People
Design
Wk 1–2
Build
Wk 3–5
Validate
Wk 6–8
Rollout
Wk 11–14 (after GO)
Gate
Wk 10
Train
Wk 6–8
Dependencies: Design → Build → Validate · Build → Train · Validate AND Train → Gate (Week 10) · Gate GO → Rollout (Weeks 11–14)

## Slide 7
R5 (backup power) is now the top exposure at 15; every risk
has a named mitigation
Likelihood and impact on 1–5 scales; exposure = L × I
5
4
3
2
1
1 2 3 4 5
Likelihood (1–5) →
↑ Impact (1–5)
R1
R2
R3
R4
R5
ID | Likelihood | Impact | L × I | Mitigation
R1 | 4 | 3 | 12 | Cross-train two crews
R2 | 2 | 5 | 10 | Dual-source hardware
R3 | 3 | 4 | 12 | Test failover weekly
R4 | 2 | 2 | 4 | Audit labels
R5 | 3 | 5 | 15 | Test backup power before gate

## Slide 8
Approve $440k for Resilient now; release rollout only on a
Week 10 GO
Gate at Week 10 requires all three thresholds; any single failure means HOLD
Approve $440k today
Build & train Wk 1–8
Gate: Week 10
Rollout Wk 11–14 on GO
Uptime ≥ 99.5%
Resilient design is 99.8%; measured uptime must reach 99.5%
All 5 sites ≥ 95% on time
Today 2 of 5 pass (Central 96%, South 97%)
Backup-power test passed
Pass/fail result required at the Week 10 gate (R5 mitigation)
GO (all three pass): start rollout in Weeks 11–14; base case pays back in 2.8 years, +$25k over three years
HOLD (any threshold fails): no rollout; fix the failing threshold, re-test and return to this committee