## Slide 1
Recommendation: fund the Balanced option — $350k returns $130k a year and pays back in 2.7 years
$350k
Investment (one-time)
$130k
Annual saving
2.7 yrs
Simple payback (350 ÷ 130)
+$40k
Three-year net (3 × 130 − 350)
Why Balanced
• Output trails target every month: 5,460 vs 5,960 readings over M1–M6 (−500)
• Middle option: 8-week lead time, 99.0% rated uptime, $90k below Resilient
• Thin margin: three-year net is +$40k at base but −$38k in the 80% downside
• Rollout (weeks 9–12) proceeds only if the week-8 gate passes
DECISION REQUESTED
Approve $350k for Balanced now.
GO to rollout at week 8 only if uptime ≥99.5%, all five sites ≥95% on time and the backup-power test passes; otherwise HOLD.
Cedar sensor network · field sensor rollout · engineering steering group · synthetic data · 1/8

## Slide 2
Output missed target in all six months: 5,460 vs 5,960 readings, a 500-reading gap
Monthly sensor readings, actual vs target, M1–M6
Chart: 
| M1 | M2 | M3 | M4 | M5 | M6
Actual | 890 | 890 | 940 | 980 | 860 | 900
Target | 970 | 980 | 1070 | 1040 | 930 | 970
5,460
Total actual readings, M1–M6
5,960
Total target readings, M1–M6
−500
Gap: 8.4% below target; largest miss M3 (−130)
Cedar sensor network · field sensor rollout · synthetic data · 2/8

## Slide 3
Balanced trades Lean's faster payback for higher uptime and avoids Resilient's $440k cost
Reference option prices unchanged · payback = investment ÷ saving · 3-yr net = 3 × saving − investment
Option | Investment $k | Saving $k/yr | Uptime % | Lead weeks | Payback yrs | 3-yr net $k
Lean | 210 | 95 | 97.5 | 6 | 2.2 | +75
Balanced (selected) | 350 | 130 | 99.0 | 8 | 2.7 | +40
Resilient | 440 | 155 | 99.8 | 10 | 2.8 | +25
vs Lean
+$140k buys +$35k/yr saving and +1.5 pts uptime; payback slips 2.2 → 2.7 yrs and 3-yr net falls $75k → $40k.
vs Resilient
$90k less and 2 weeks faster; gives up $25k/yr saving and 0.8 pts uptime. 3-yr net $40k vs $25k.
Tradeoff to watch
Rated 99.0% uptime is 0.5 pt below the 99.5% gate threshold; validation must close it or the decision is HOLD.
Cedar sensor network · field sensor rollout · synthetic data · 3/8

## Slide 4
Payback ranges 2.2–3.4 years; at 80% of base saving the three-year net turns negative
Annual saving by scenario, $k/yr (80 / 100 / 120% of Balanced $130k) · investment fixed at $350k
Chart: 
| Downside 80% | Base 100% | Upside 120%
Annual saving $k | 104 | 130 | 156
Scenario | Saving $k/yr | Payback yrs | 3-yr net $k
Downside 80% | 104 | 3.4 | −38
Base 100% | 130 | 2.7 | +40
Upside 120% | 156 | 2.2 | +118
Three-year break-even
Needs ≥ $117k/yr (≈90% of base). Base clears it by $13k/yr; the downside falls short by $13k/yr.
Cedar sensor network · field sensor rollout · synthetic data · 4/8

## Slide 5
Daily demand of 1,700 exceeds capacity of 1,660; North, Central and West are capacity-constrained
Readings per day by site (daily rates, not six-month totals) · gap = capacity − demand
Site | Demand/day | Capacity/day | On time % | Owner | Gap/day | Status
North | 400 | 360 | 91 | Ari | −40 | Constrained
Central | 400 | 320 | 96 | Bo | −80 | Constrained
South | 260 | 320 | 97 | Cy | +60 | Spare
East | 290 | 360 | 89 | Dee | +70 | Spare
West | 350 | 300 | 92 | Eli | −50 | Constrained
Total | 1,700 | 1,660 | — | — | −40 | Short
Capacity-constrained
North −40/day
Central −80/day
West −50/day
South and East have spare.
Gate exposure
Only Central (96%) and South (97%) meet ≥95% on time; North, East and West must improve by week 8.
Cedar sensor network · field sensor rollout · synthetic data · 5/8

## Slide 6
Rollout starts in week 9 only after Validate and Train both clear the week-8 gate
Wk 1–2
Wk 3–5
Wk 6–8
Wk 9–12
Technical
Decision
People
Design · Wk 1–2
after: none
Build · Wk 3–5
after: Design
Validate · Wk 6–8
after: Build
Rollout · Wk 9–12
after: Gate GO
GATE · Wk 8
GO / HOLD
Train · Wk 6–8
after: Build
Dependencies: Design → Build → Validate; Build → Train; Validate AND Train → Gate (wk 8); Gate GO → Rollout (wk 9–12). Any failed threshold = HOLD.
Cedar sensor network · field sensor rollout · synthetic data · 6/8

## Slide 7
R1 and R3 carry the highest exposure (score 12); every risk has a named mitigation
5
4
3
2
1
1
2
3
4
5
Likelihood (1–5) →
Impact
(1–5)
↑
R1
R2
R3
R4
ID | Likelihood | Impact | Score L×I | Mitigation
R1 | 4 | 3 | 12 | Cross-train two crews
R2 | 2 | 5 | 10 | Dual-source hardware
R3 | 3 | 4 | 12 | Test failover weekly
R4 | 2 | 2 | 4 | Audit labels
Priority: R1 (L4 × I3) and R3 (L3 × I4) both score 12. R2 is unlikely but severe (impact 5). R4 is low (score 4). Score = likelihood × impact.

## Slide 8
Decision: approve $350k for Balanced now; release rollout at week 8 only if all three thresholds pass
NOW
Approve $350k · Balanced
WEEK 8 · GATE
Go / no-go review
WEEKS 9–12
Rollout if GO
Gate threshold (all must pass) | Required | Status today
Uptime | ≥ 99.5% | Balanced rated 99.0%
On-time delivery | All five sites ≥ 95% | 2 of 5 meet (Central, South)
Backup-power test | Passed | Required by week 8
HOLD if any threshold fails
Rollout does not start in week 9; return to this group with the failed threshold and a fix plan.
GO (all three pass) → rollout weeks 9–12. Case: payback 2.7 yrs, three-year net +$40k (−$38k in the 80% downside).
Cedar sensor network · field sensor rollout · synthetic data · 8/8