## Slide 1
Recommend Balanced: fund the Cedar sensor network now
Field sensor rollout • Decision for the engineering steering group • All data synthetic • Currency: $k
DECISION: Approve Balanced — $350k investment, subject to the Week 8 gate (Slide 8).
ANNUAL SAVING
$130k / yr
SIMPLE PAYBACK
2.7 years
THREE-YEAR NET SAVING
$40k
Payback = $350k ÷ $130k/yr = 2.7 years. Three-year net = 3 × $130k − $350k = $40k. Balanced closes most of the performance gap without the cost and lead time of Resilient.
1 • Executive recommendation

## Slide 2
Six months: actual trails target by 500 readings in every period
Readings per month (M1–M6) — actual vs target
Chart: 
| M1 | M2 | M3 | M4 | M5 | M6
Actual | 890 | 890 | 940 | 980 | 860 | 900
Target | 970 | 980 | 1070 | 1040 | 930 | 970
SIX-MONTH TOTALS
Total actual
5,460 readings
Total target
5,960 readings
Gap
−500 readings
Actual: 890, 890, 940, 980, 860, 900 • Target: 970, 980, 1,070, 1,040, 930, 970 • The persistent shortfall is the problem the investment must fix.
2 • Actual vs target

## Slide 3
Balanced is the middle path: +$35k/yr over Lean, $90k less than Resilient
Option | Investment $k | Saving $k/yr | Uptime % | Lead weeks
Lean | 210 | 95 | 97.5 | 6
Balanced | 350 | 130 | 99.0 | 8
Resilient | 440 | 155 | 99.8 | 10
Selected option — Balanced: the tradeoff
Balanced costs $140k more than Lean and takes 2 weeks longer, but raises uptime from 97.5% to 99.0% and saving from $95k to $130k/yr. Resilient adds only $25k/yr and 0.8 pts of uptime for another $90k and 2 more weeks — diminishing returns. Balanced accepts slightly lower uptime than Resilient in exchange for earlier delivery and lower capital at risk.
3 • Options • Reference prices unchanged

## Slide 4
Even at 80% saving, Balanced nearly breaks even in three years
Annual saving by scenario — $k/yr (80% / 100% / 120% of $130k)
Chart: 
| Downside 80% | Base 100% | Upside 120%
Annual saving $k/yr | 104 | 130 | 156
PAYBACK & 3-YEAR NET ($350k invested)
Downside 80% — $104k/yr
Payback 3.4 yrs • 3-yr net −$38k
Base 100% — $130k/yr
Payback 2.7 yrs • 3-yr net $40k
Upside 120% — $156k/yr
Payback 2.2 yrs • 3-yr net $118k
Payback = $350k ÷ saving. Three-year net = 3 × saving − $350k. Downside risk is bounded at −$38k over three years.
4 • Scenarios

## Slide 5
Three of five sites are capacity-constrained today
Daily demand vs daily capacity by site (not six-month totals)
Site | Demand/day | Capacity/day | On time % | Owner
North | 400 | 360 | 91 | Ari
Central | 400 | 320 | 96 | Bo
South | 260 | 320 | 97 | Cy
East | 290 | 360 | 89 | Dee
West | 350 | 300 | 92 | Eli
Totals: Demand 1,700/day
Capacity 1,660/day • Shortfall 40/day
Capacity-constrained (demand > capacity):
North, Central, West
5 • Sites

## Slide 6
12-week roadmap: build and train converge at the Week 8 gate
TECHFICAL
PEOPLE
Design
Wks 1–2
Dep: None
Build
Wks 3–5
Dep: Design
Validate
Wks 6–8
Dep: Build
Train
Wks 6–8
Dep: Build
DECISION
Gate Wk 8
Validate
AND Train
Rollout
Wks 9–12
Dep: Gate GO
Sequence: Design (1–2) → Build (3–5) → Validate (6–8) and Train (6–8) in parallel → Gate at Week 8 → Rollout (9–12) only on GO. No rollout before the gate.
6 • Roadmap

## Slide 7
Top risks are R1 and R3; R2 is low-likelihood but highest impact
1 2 3 4 5
Impact (1–5) →
5
4
3
2
1
L
i
k
e
l
i
h
o
o
d
R1
R2
R3
R4
MITIGATIONS (all risks)
R1 L4 × I3 — Cross-train two crews
R2 L2 × I5 — Dual-source hardware
R3 L3 × I4 — Test failover weekly
R4 L2 × I2 — Audit labels
7 • Risks • Likelihood (vertical) × Impact (horizontal)

## Slide 8
Fund $350k now; rollout only if every Week 8 threshold passes
FUNDING DECISION — GO
Approve Balanced: $350k investment
$130k/yr saving • 2.7-yr payback
FALLBACK — HOLD
If ANY threshold fails: HOLD.
No rollout. Fix, re-test, re-gate.
GO / NO-GO GATE — Week 8 (all three thresholds must pass)
1) Uptime ≥ 99.5% 2) All five sites ≥ 95% on time 3) Backup-power test passed
Gate rule: Uptime ≥99.5% AND all five sites ≥95% on time AND backup-power test passed.
Next step on GO: Rollout in Weeks 9–12 to all five sites. On HOLD: pause rollout, remediate the failed threshold, and repeat the Week 8 gate before any rollout.
8 • Funding & decision • Cedar sensor network — Balanced