## Slide 1
CEDAR SENSOR NETWORK / ENGINEERING STEERING GROUP
Recommend Balanced; release rollout only after the week-8 gate
Authorize the $350k investment for the field sensor rollout, with deployment conditional on measured readiness.
$130k
Annual saving · base case
2.7 years
Simple payback
$40k
Three-year net saving
The recommendation carries a readiness condition
Balanced reference uptime is 99.0%, below the 99.5% gate. Validate performance and all site thresholds before a GO.
Synthetic decision case · Currency: $k · Payback = investment / annual saving · Three-year net = 3 × saving − investment
01 / 08

## Slide 2
Six-month readings missed target by 500
Actual delivery reached 91.6% of target; every month finished below plan.
Chart: 
| M1 | M2 | M3 | M4 | M5 | M6
Actual | 890 | 890 | 940 | 980 | 860 | 900
Target | 970 | 980 | 1070 | 1040 | 930 | 970
Readings per month
5,460
Total actual readings
5,960
Total target readings
500
Shortfall
Target − actual
Synthetic data · Six-month totals are readings; site demand and capacity later in the deck are daily measures.
02 / 08

## Slide 3
Balanced buys more saving than Lean, but uptime remains a
gate
Reference option prices and performance remain unchanged; Balanced is the selected investment.
Option | Investment $k | Saving $k/yr | Uptime % | Lead weeks
Lean | 210 | 95 | 97.5 | 6
Balanced | 350 | 130 | 99.0 | 8
Resilient | 440 | 155 | 99.8 | 10
SELECTED: BALANCED
Versus Lean: $140k more investment buys $35k more annual saving and 1.5 points of uptime.
TRADEOFF TO ACCEPT
Resilient costs $90k more, saves $25k more annually and adds 0.8 uptime points, with 2 more lead weeks.
Synthetic reference options · Balanced uptime of 99.0% does not establish compliance with the 99.5% rollout gate.
03 / 08

## Slide 4
The downside case turns three-year net saving negative
Savings sensitivity uses 80%, 100% and 120% of Balanced’s $130k annual saving; investment stays $350k.
Annual saving ($k/year)
Chart: 
| Downside 80% | Base 100% | Upside 120%
Annual saving | 104 | 130 | 156
Scenario | Payback years | 3-year net $k
Downside | 3.4 | −38
Base | 2.7 | 40
Upside | 2.2 | 118
A 20% saving reduction extends payback to 3.4 years and yields a $38k three-year net loss.
Synthetic sensitivity · Simple payback = 350 / annual saving, rounded to 1 decimal · Three-year net = 3 × annual saving − 350
04 / 08

## Slide 5
North, Central and West are capacity-constrained
Total daily demand exceeds capacity by 40; site-level bottlenecks require attention even where on-time service is high.
Site | Demand/day | Capacity/day | On time % | Owner
North | 400 | 360 | 91 | Ari
Central | 400 | 320 | 96 | Bo
South | 260 | 320 | 97 | Cy
East | 290 | 360 | 89 | Dee
West | 350 | 300 | 92 | Eli
Total | 1,700 | 1,660 | — | —
Daily capacity deficits: North 40 · Central 80 · West 50
Below the 95% on-time gate: North, East and West
Synthetic site data · Demand and capacity are daily readings, not six-month totals · Each site must reach ≥95% on time.
05 / 08

## Slide 6
Validate and Train must both finish before the week-8 gate
Connected Technical and People lanes; rollout in weeks 9–12 depends on a GO decision.
Technical
People
Design
Weeks 1–2
Build
Weeks 3–5
Validate
Weeks 6–8
Train
Weeks 6–8
Decision
gate
Week 8
Rollout
Weeks 9–12
GO
Dependencies: Design has none; Build follows Design; Validate and Train follow Build; Gate requires both; Rollout requires Gate GO.
Synthetic delivery plan · Connections show prerequisite → dependent activity. 06 / 08

## Slide 7
R1 is most likely; R2 has the highest impact
Risk coordinates use likelihood and impact on 1–5 scales; mitigations cover all four identified risks.
Likelihood (1 = low; 5 = high)
5
4
3
2
1
1
2
3
4
5
Impact (1 = low; 5 = high) →
R1
R2
R3
R4
Risk · L / I | Mitigation
R1 · 4 / 3 | Cross-train two crews
R2 · 2 / 5 | Dual-source hardware
R3 · 3 / 4 | Test failover weekly
R4 · 2 / 2 | Audit labels

## Slide 8
Approve $350k for Balanced; make rollout a conditional GO
The steering group funds the selected option now and makes the deployment decision at the end of week 8.
FUNDING REQUEST
$350k
Balanced
Cedar sensor network
Base case
$130k annual saving
2.7-year payback
$40k three-year net
WEEK 8: GO ONLY IF ALL THREE PASS
1 Uptime ≥99.5%
2 All five sites ≥95% on time
3 Backup-power test passed
ALL PASS → GO
Proceed to the next rollout in weeks 9–12.
ANY FAIL → HOLD
Remediate and re-test; defer rollout until all pass.
Synthetic decision case · The 99.0% Balanced reference uptime is below the gate; demonstrated readiness is required.
08 / 08