## Slide 1
CEDAR SENSOR NETWORK / ENGINEERING STEERING GROUP
Choose Resilient: uptime now takes priority over price
Approve $440k for the field sensor rollout. Release deployment only after the week-10 readiness gate passes.
RESILIENT INVESTMENT
$440k
ANNUAL SAVING
$155k
SIMPLE PAYBACK
2.8 years
THREE-YEAR NET SAVING
$25k = 3 × $155k − $440k
99.8% reference uptime
Resilient exceeds the 99.5% gate by 0.3 percentage points. Validate actual uptime, site service and backup power before GO.
01 / Fictional committee • All data synthetic • Currency throughout: $k

## Slide 2
PERFORMANCE / SIX-MONTH DELIVERY
M4 beats target, but six-month delivery remains 330 short
Monthly readings • Corrected M4 actual: 1,150
Chart: 
| M1 | M2 | M3 | M4 | M5 | M6
Actual | 890 | 890 | 940 | 1150 | 860 | 900
Target | 970 | 980 | 1070 | 1040 | 930 | 970
SIX-MONTH TOTALS
5,630 actual
5,960 target
330 short
5.5% below target
02 / All data synthetic • All 12 monthly values shown • Units: readings

## Slide 3
OPTIONS / UNCHANGED REFERENCE VALUES
Resilient alone exceeds the 99.5% uptime threshold
Uptime now outranks price; reference prices, savings and lead times remain unchanged.
Option | Investment $k | Saving $k/yr | Uptime % | Lead weeks
Lean | 210 | 95 | 97.5 | 6
Balanced | 350 | 130 | 99.0 | 8
Resilient | 440 | 155 | 99.8 | 10
SELECTED: RESILIENT
Versus Balanced: +$90k investment, +2 lead weeks and +$25k annual saving.
The tradeoff
Pay more and wait longer for 99.8% reference uptime; prove readiness at the gate.
03 / All data synthetic • Reference uptime informs selection; measured performance determines release

## Slide 4
ECONOMICS / RESILIENT SAVINGS SENSITIVITY
The base case yields $25k net; downside falls to −$68k
Annual saving ($k) • Fixed investment: $440k
Chart: 
| Downside 80% | Base 100% | Upside 120%
Annual saving $k | 124 | 155 | 186
Scenario | Payback years | 3-year net $k
Downside 80% | 3.5 | −68
Base 100% | 2.8 | 25
Upside 120% | 2.4 | 118
At 80% of expected saving, investment is not recovered within three years.
04 / Synthetic data • Payback = investment ÷ annual saving, rounded to 0.1 year • 3-year net = 3 × saving − investment

## Slide 5
SITE READINESS / DAILY OPERATING LOAD
North, Central and West are capacity-constrained
Site | Demand/day | Capacity/day | On time % | Owner
North | 400 | 360 | 91 | Ari
Central | 400 | 320 | 96 | Bo
South | 260 | 320 | 97 | Cy
East | 290 | 360 | 89 | Dee
West | 350 | 300 | 92 | Eli
DAILY TOTALS
1,700
demand
1,660
capacity
40/day net gap
Daily capacity deficits: North 40; Central 80; West 50.
North, East and West also fall below the unchanged ≥95% on-time gate.
05 / All data synthetic • Demand and capacity are daily readings, separate from six-month performance totals

## Slide 6
EXECUTION / TWO-LANE DEPENDENCY ROADMAP
Validate and Train feed the week-10 decision gate
Technical
People
Design
Weeks 1–2
Build
Weeks 3–5
Validate
Weeks 6–8
Train
Weeks 6–8
Decision
Gate
Week 10
Rollout
Weeks
11–14
Dependencies run left to right. Design: none. Build → Validate and Train.
Gate requires Validate AND Train. Rollout requires Gate GO.
06 / All data synthetic • Weeks relative to project start • Design, Build, Validate and Train timing unchanged

## Slide 7
RISK / LIKELIHOOD AND IMPACT
R2 and R5 have maximum impact; test backup power early
Impact ↑ 1 low to 5 high
Impact | 1 | 2 | 3 | 4 | 5
5 |  | R2 | R5 |  | 
4 |  |  | R3 |  | 
3 |  |  |  | R1 | 
2 |  | R4 |  |  | 
1 |  |  |  |  | 
Likelihood → 1 low to 5 high
MITIGATIONS / (LIKELIHOOD, IMPACT)
R1 (4, 3) Cross-train two crews
R2 (2, 5) Dual-source hardware
R3 (3, 4) Test failover weekly
R4 (2, 2) Audit labels
R5 (3, 5)
Test backup power before gate
07 / All data synthetic • R1–R4 unchanged • Risk IDs occupy their specified likelihood/impact cells

## Slide 8
DECISION / FUNDING AND RELEASE CONDITIONS
Fund Resilient at $440k; require all thresholds for GO
FUNDING REQUEST
$440k
Resilient option
Base case
$155k annual saving
2.8-year payback
$25k three-year net
WEEK 10 / ALL THREE CONDITIONS MUST PASS
1 Uptime ≥99.5%
2 All five sites ≥95% on time
3 Backup-power test passed
GO: every threshold passes
Next rollout: weeks 11–14
HOLD: any threshold fails
Remediate and repeat the gate
08 / All data synthetic • Gate prerequisites: Validate AND Train • Funding approval precedes operational release