## Slide 1
Fund Resilient: $440k saves $155k/yr, pays back in 2.8 years
Aster cold-chain · regional distribution capacity · operations committee decision · synthetic data
$440k
Investment
Resilient option
$155k/yr
Annual saving
base case
2.8 yrs
Simple payback
440 ÷ 155
+$25k
Three-year net
3 × 155 − 440
Why act now
• Shipments 520 (9.2%) below six-month target: 5,150 vs 5,670
• South demand of 340/day exceeds its 320/day capacity
• Uptime now outranks price: only Resilient (99.8%) is rated above the 99.5% gate
Decision requested
Fund $440k for Resilient today.
Go/no-go gate at week 10; rollout weeks 11–14 only on GO, otherwise HOLD.

## Slide 2
Shipments missed target in five of six months, 520 short overall
Monthly gaps: M1 −80 · M2 −120 · M3 −120 · M4 +40 · M5 −100 · M6 −140
Shipments per month, actual vs target
Chart: 
| M1 | M2 | M3 | M4 | M5 | M6
Target | 950 | 970 | 840 | 1040 | 820 | 1050
Actual | 870 | 850 | 720 | 1080 | 720 | 910
5,150
Total actual shipments
5,670
Total target shipments
−520
Gap (9.2% below target)
Only M4 beat target (+40). Largest shortfall: M6 at −140

## Slide 3
Resilient is the only option rated above the 99.5% uptime gate
Reference option values unchanged; Resilient is now selected because uptime outranks price
Option | Investment $k | Saving $k/yr | Uptime % | Lead weeks | Payback yrs | 3-yr net $k
Lean | 220 | 95 | 97.5 | 6 | 2.3 | 65
Balanced | 350 | 130 | 99.0 | 8 | 2.7 | 40
Resilient (selected) | 440 | 155 | 99.8 | 10 | 2.8 | 25
Payback = investment ÷ annual saving (one decimal). 3-yr net = 3 × saving − investment.
The tradeoff
vs Balanced: +$90k cost, +$25k/yr saving, +0.8 pts uptime, 2 weeks longer; payback 0.1 yr longer, 3-yr net $15k lower.
vs Lean: +$220k cost, +2.3 pts uptime, 4 weeks longer; 3-yr net $40k lower.
Why accept it: 99.8% is the only rating that clears the 99.5% gate threshold.

## Slide 4
Base case clears three-year breakeven by $25k; downside misses it
Scenarios at 80 / 100 / 120% of Resilient's $155k/yr saving; $440k investment
Annual saving by scenario, $k/yr
Chart: 
| Downside 80% | Base 100% | Upside 120%
Annual saving $k/yr | 124 | 155 | 186
Scenario | Saving $k/yr | Payback yrs | 3-yr net $k
Downside 80% | 124 | 3.5 | −68
Base 100% | 155 | 2.8 | +25
Upside 120% | 186 | 2.4 | +118
Three-year breakeven needs ≥$147k/yr (440 ÷ 3). Downside is ≈$23k/yr short, so the week-10 gate must confirm performance before rollout spend.

## Slide 5
South is the only site where daily demand exceeds capacity
Daily shipments by site; headroom = capacity − demand
Site | Demand/day | Capacity/day | Headroom/day | On time % | Owner
North | 340 | 380 | +40 | 95 | Ari
Central | 290 | 330 | +40 | 94 | Bo
South | 340 | 320 | −20 | 89 | Cy
East | 320 | 340 | +20 | 94 | Dee
West | 310 | 340 | +30 | 96 | Eli
Total | 1,600 | 1,710 | +110 | — | —
1,600 / 1,710
Total daily demand / capacity (94% utilized)
Capacity-constrained:
South (−20/day)
Below 95% on-time gate: Central 94, South 89, East 94

## Slide 6
Rollout moves to weeks 11–14, after Validate and Train clear the week-10 gate
Critical path: Design → Build → Validate → Gate → Rollout; Train runs alongside Validate
W1
W6
W10
W14
Technical
Decision
People
Design
W1–2
No dependency
Build
W3–5
After Design
Validate
W6–8
After Build
Rollout
W11–14
After Gate GO
Gate
W10
Go/no-go gate, week 10
needs Validate AND Train
Train
W6–8
After Build

## Slide 7
New backup-power risk R5 scores highest at 15; every risk has a mitigation
R1
R2
R3
R4
R5
1
2
3
4
5
5
4
3
2
1
Likelihood (1–5) →
↑
Impact
(1–5)
ID | Likelihood × Impact | Mitigation
R1 | 4 × 3 = 12 | Cross-train two crews
R2 | 2 × 5 = 10 | Dual-source hardware
R3 | 3 × 4 = 12 | Test failover weekly
R4 | 2 × 2 = 4 | Audit labels
R5 | 3 × 5 = 15 | Test backup power before gate

## Slide 8
Approve $440k now; roll out after week 10 only if all thresholds pass
One funding decision today, one go/no-go decision at the week-10 gate
1 · Fund today
$440k
Resilient
$155k/yr saving
2.8-yr payback
+$25k three-year net
2 · Week-10 gate: all three must pass
Uptime ≥ 99.5%
Resilient is rated 99.8%
All five sites ≥ 95% on time
Today 2 of 5 meet it (North, West)
Backup-power test passed
Required at gate; tested early under R5
GO — all pass
Roll out weeks 11–14
HOLD — any one fails
No rollout until the committee reviews again
Ask: approve $440k for Resilient today and confirm the three thresholds as the binding week-10 go/no-go criteria.