## Slide 1
Choose Resilient: uptime now leads the investment decision
Aster cold-chain | Regional distribution capacity | Operations committee
Approve $440k for Resilient; make rollout conditional on the week 10 gate.
$440k
Chosen investment
$155k
Annual saving
2.8 years
Simple payback
$25k
Three-year net saving
Prioritize uptime
Resilient lists 99.8% uptime. Its $90k premium over Balanced buys 0.8 percentage points.
Close service gaps
Actual shipments are 520 below six-month target. South is the capacity-constrained site.
Control the release
Require every threshold at week 10. GO enables weeks 11–14 rollout; any failure means HOLD.
Synthetic data. Currency: $k. Payback = investment / annual saving; three-year net = 3 × saving − investment. 1 / 8

## Slide 2
The corrected six-month shipment shortfall is 520
M4 exceeds target by 40; the other five months miss. Total actual is 9.2% below target.
Monthly shipments | All 12 values shown
Chart: 
| M1 | M2 | M3 | M4 | M5 | M6
Actual | 870 | 850 | 720 | 1080 | 720 | 910
Target | 950 | 970 | 840 | 1040 | 820 | 1050
5,150
Total actual shipments
5,670
Total target shipments
−520
Actual minus target
M4 actual corrected to 1,080 shipments. Targets are unchanged. Daily site figures are separate from these period totals. 2 / 8

## Slide 3
Resilient buys the highest listed uptime for a $90k premium
Selected option: Resilient. All reference prices, savings, uptime specifications and lead times remain unchanged.
Option | Investment $k | Saving $k/yr | Uptime % | Lead weeks
Lean | 220 | 95 | 97.5 | 6
Balanced | 350 | 130 | 99.0 | 8
Resilient | 440 | 155 | 99.8 | 10
Tradeoff versus Balanced
Pay $90k more for 0.8 points more uptime and $25k more annual saving. Lead time rises by two weeks; three-year net saving falls from $40k to $25k.
Uptime is the priority
Only Resilient lists uptime above the 99.5% gate. Demonstrated performance must still pass.
Listed uptime is a reference specification, not evidence that the operational release gate has passed. 3 / 8

## Slide 4
Resilient delivers $25k three-year net saving in the base case
Investment stays at $440k; downside, base and upside savings are 80%, 100% and 120% of $155k.
Annual saving ($k/year)
Chart: 
| Downside 80% | Base 100% | Upside 120%
Annual saving | 124 | 155 | 186
Returns at the same $440k investment
Scenario | Payback years | 3-year net $k
Downside 80% | 3.5 | −68
Base 100% | 2.8 | 25
Upside 120% | 2.4 | 118
Downside loses $68k over three years.
Break-even saving: $146.7k/year.
Payback = 440 / annual saving, rounded to one decimal year. Three-year net = 3 × annual saving − 440. 4 / 8

## Slide 5
South is capacity-constrained despite network headroom
Daily site figures reveal a local bottleneck; three sites also fall below the 95% on-time gate.
Site | Demand/day | Capacity/day | On time % | Owner
North | 340 | 380 | 95 | Ari
Central | 290 | 330 | 94 | Bo
South | 340 | 320 | 89 | Cy
East | 320 | 340 | 94 | Dee
West | 310 | 340 | 96 | Eli
1,600
Total demand / day
1,710
Total capacity / day
Capacity-constrained: South, short 20/day.
Network headroom: 110/day.
Below 95% on time: Central, South and East.
Demand and capacity are daily shipments; they are distinct from the six-month shipment totals on slide 2. 5 / 8

## Slide 6
Both delivery lanes must clear the week 10 decision gate
Design, Build, Validate and Train retain their weeks. Gate GO enables rollout in weeks 11–14.
Technical
People
Design
Weeks 1–2
Deps: none
Build
Weeks 3–5
After Design
Validate
Weeks 6–8
After Build
Train
Weeks 6–8
After Build
Decision gate
Week 10
Validate
AND Train
GO / HOLD
Rollout
Weeks 11–14
After Gate GO
Read dependencies left to right. Validate AND Train are required; all gate thresholds must also pass.
Gate moves to week 10; rollout moves to weeks 11–14. Gate criteria appear on slide 8. 6 / 8

## Slide 7
R5 adds a maximum-impact risk: test backup power before gate
Likelihood increases left to right; impact increases upward. Ratings use a 1–5 scale.
Impact ↑ | 5 = highest
Impact | 1 | 2 | 3 | 4 | 5
5 |  | R2 | R5 |  | 
4 |  |  | R3 |  | 
3 |  |  |  | R1 | 
2 |  | R4 |  |  | 
1 |  |  |  |  | 
Likelihood → | 1 low to 5 high
Mitigations for all five risks
Risk (likelihood, impact) | Mitigation
R1 (4, 3) | Cross-train two crews
R2 (2, 5) | Dual-source hardware
R3 (3, 4) | Test failover weekly
R4 (2, 2) | Audit labels
R5 (3, 5) | Test backup power before gate
R5: likelihood 3, impact 5; complete before week 10.
R1–R4 ratings and mitigations are unchanged. Each risk ID occupies its likelihood column and impact row. 7 / 8

## Slide 8
Approve $440k; release rollout only after the week 10 gate
Resilient funding | $155k annual saving | 2.8-year payback | $25k three-year net saving
Week 10 gate: ALL conditions must pass
Condition | GO threshold
Uptime | At least 99.5%
On-time service | All five sites at least 95% each
Backup power | Backup-power test passed
GO: every threshold passes
Authorize the next rollout across all five sites in weeks 11–14.
HOLD: any threshold fails
Pause rollout, remediate, then repeat the gate before release.
Prerequisites: Validate AND Train, both weeks 6–8.
Confirm uptime in operation, lift Central/South/East to 95% on time, and pass the backup-power test.
All data are synthetic. Funding approval does not replace the week 10 release gate. 8 / 8