## Slide 1
CEDAR SENSOR NETWORK / ENGINEERING STEERING GROUP
Recommend Balanced, with rollout conditional on the week-8 gate
Approve a $350k investment for the field sensor rollout; require measured operational readiness before release.
CHOSEN INVESTMENT
$350k
ANNUAL SAVING
$130k
SIMPLE PAYBACK
2.7 years
THREE-YEAR NET SAVING
$40k = 3 × $130k − $350k
Critical condition
Balanced's reference uptime is 99.0%, below the 99.5% gate. The recommendation depends on closing and validating that gap.
01 / Fictional committee • All data synthetic • Currency throughout: $k

## Slide 2
PERFORMANCE / SIX-MONTH DELIVERY
Actual delivery missed target in every month
Monthly readings • All 12 actual and target values shown
Chart: 
| M1 | M2 | M3 | M4 | M5 | M6
Actual | 890 | 890 | 940 | 980 | 860 | 900
Target | 970 | 980 | 1070 | 1040 | 930 | 970
SIX-MONTH TOTALS
5,460 actual
5,960 target
500 short
8.4% below target
02 / All data synthetic • Monthly and total units: readings

## Slide 3
OPTIONS / UNCHANGED REFERENCE PRICES
Balanced trades lower cost and lead time for an uptime gap
Option | Investment $k | Saving $k/yr | Uptime % | Lead weeks
Lean | 210 | 95 | 97.5 | 6
Balanced | 350 | 130 | 99.0 | 8
Resilient | 440 | 155 | 99.8 | 10
SELECTED: BALANCED
Saves $90k of investment and 2 lead weeks versus Resilient, while giving up $25k/year of saving.
Tradeoff to resolve
99.0% reference uptime is 0.5 percentage points below the 99.5% release gate.
03 / All data synthetic • Reference option prices and specifications remain unchanged

## Slide 4
ECONOMICS / SAVINGS SENSITIVITY
The downside case does not recover investment in three years
Annual saving ($k) • Fixed investment: $350k
Chart: 
| Downside 80% | Base 100% | Upside 120%
Annual saving $k | 104 | 130 | 156
Scenario | Payback years | 3-year net $k
Downside 80% | 3.4 | −38
Base 100% | 2.7 | 40
Upside 120% | 2.2 | 118
Base case creates $40k net over three years; downside loses $38k over the same period.
04 / Synthetic data • Payback = investment ÷ annual saving; 3-year net = 3 × annual saving − investment

## Slide 5
SITE READINESS / DAILY OPERATING LOAD
North, Central and West have insufficient daily capacity
Site | Demand/day | Capacity/day | On time % | Owner
North | 400 | 360 | 91 | Ari
Central | 400 | 320 | 96 | Bo
South | 260 | 320 | 97 | Cy
East | 290 | 360 | 89 | Dee
West | 350 | 300 | 92 | Eli
DAILY TOTALS
1,700
demand
1,660
capacity
40/day net gap
Capacity deficits: North 40/day; Central 80/day; West 50/day. On-time gate failures: North, East and West.
05 / All data synthetic • Demand and capacity are daily readings, separate from the six-month totals

## Slide 6
EXECUTION / TWO-LANE DEPENDENCY ROADMAP
Validation and training must both finish before the week-8 gate
Technical
People
Design
Weeks 1–2
Build
Weeks 3–5
Validate
Weeks 6–8
Train
Weeks 6–8
Decision
Gate
Week 8
Rollout
Weeks 9–12
Dependencies flow left to right. Design: none. Gate requires Validate AND Train. Rollout requires Gate GO.
06 / All data synthetic • Week numbers are relative to project start

## Slide 7
RISK / LIKELIHOOD AND IMPACT
R2 has the highest impact; R1 has the highest likelihood
Impact increases upward • Scale: 1 low to 5 high
Impact | 1 | 2 | 3 | 4 | 5
5 |  | R2 |  |  | 
4 |  |  | R3 |  | 
3 |  |  |  | R1 | 
2 |  | R4 |  |  | 
1 |  |  |  |  | 
Likelihood → 1 low to 5 high
MITIGATIONS FOR EVERY RISK
R1 · (4, 3) Cross-train two crews
R2 · (2, 5) Dual-source hardware
R3 · (3, 4) Test failover weekly
R4 · (2, 2) Audit labels
07 / All data synthetic • Coordinate pairs are (likelihood, impact); IDs occupy their specified matrix cells

## Slide 8
DECISION / FUNDING AND RELEASE CONDITIONS
Fund Balanced at $350k; release rollout only if every gate passes
FUNDING REQUEST
$350k
Balanced option
Base case
$130k annual saving
2.7-year payback
$40k three-year net
WEEK 8 / ALL THREE CONDITIONS MUST PASS
1 Uptime ≥99.5%
2 All five sites ≥95% on time
3 Backup-power test passed
GO: every threshold passes
Next rollout: weeks 9–12
HOLD: any threshold fails
Remediate and repeat the gate
08 / All data synthetic • Funding approval is distinct from the week-8 operational GO decision