## Slide 1
CEDAR SENSOR NETWORK / ENGINEERING STEERING GROUP
Recommend Resilient; make rollout conditional on the week-10 gate
Approve $440k for the field sensor rollout. Uptime now outranks price; deployment requires demonstrated readiness.
$155k
Annual saving · base case
2.8 years
Simple payback
$25k
Three-year net saving
99.8% reference uptime supports the choice; the gate still applies
Resilient exceeds the 99.5% reference threshold. Confirm measured uptime, all five sites’ on-time service and the backup-power test before GO.
All data synthetic · Currency: $k · Payback = investment / saving · Three-year net = 3 × annual saving − investment
01 / 08

## Slide 2
M4 beat plan; the six-month shortfall narrows to 330
Actual delivery reached 94.5% of target. M4 was the only month above plan.
Readings per month
Chart: 
| M1 | M2 | M3 | M4 | M5 | M6
Actual | 890 | 890 | 940 | 1150 | 860 | 900
Target | 970 | 980 | 1070 | 1040 | 930 | 970
5,630
Total actual readings
5,960
Total target readings
330
Shortfall
Target − actual
Synthetic data · M4 actual revised to 1,150; all targets unchanged · Site demand and capacity are daily measures.
02 / 08

## Slide 3
Resilient wins on uptime, at a $90k premium to Balanced
Uptime now outranks price. All reference option prices, savings, uptime and lead times remain unchanged.
Option | Investment $k | Saving $k/yr | Uptime % | Lead weeks
Lean | 210 | 95 | 97.5 | 6
Balanced | 350 | 130 | 99.0 | 8
Resilient | 440 | 155 | 99.8 | 10
SELECTED: RESILIENT
99.8% reference uptime is 0.3 points above the gate and 0.8 points above Balanced.
TRADEOFF TO ACCEPT
Versus Balanced: $90k more investment buys $25k more annual saving, with 2 more lead weeks.
Synthetic reference options · Reference uptime supports selection; measured readiness must still pass the week-10 gate.
03 / 08

## Slide 4
A 20% saving reduction produces a $68k three-year loss
Resilient sensitivity uses 80%, 100% and 120% of $155k annual saving; investment remains $440k.
Annual saving ($k/year)
Chart: 
| Downside 80% | Base 100% | Upside 120%
Annual saving | 124 | 155 | 186
Scenario | Payback years | 3-year net $k
Downside | 3.5 | −68
Base | 2.8 | 25
Upside | 2.4 | 118
Downside payback extends to 3.5 years. The base case delivers a modest $25k three-year net saving.
Synthetic sensitivity · Payback = 440 / annual saving, rounded to 1 decimal · Three-year net = 3 × annual saving − 440
04 / 08

## Slide 5
North, Central and West are capacity-constrained
Daily demand exceeds total capacity by 40 readings; local bottlenecks also require attention.
Site | Demand/day | Capacity/day | On time % | Owner
North | 400 | 360 | 91 | Ari
Central | 400 | 320 | 96 | Bo
South | 260 | 320 | 97 | Cy
East | 290 | 360 | 89 | Dee
West | 350 | 300 | 92 | Eli
Total | 1,700 | 1,660 | — | —
Daily deficits: North 40 · Central 80 · West 50 readings
Below 95% on time:
North, East and West
Synthetic site data · Demand and capacity are daily readings, not six-month totals · Every site must reach ≥95% on time.
05 / 08

## Slide 6
Validate and Train both feed the week-10 decision gate
Activity weeks stay fixed through validation and training; a GO releases rollout in weeks 11–14.
Technical
People
Design
Weeks 1–2
Build
Weeks 3–5
Validate
Weeks 6–8
Train
Weeks 6–8
Decision
gate
Week 10
Rollout
Weeks 11–14
GO
Dependencies: Design has none. Build follows Design; Validate and Train follow Build. Gate requires both; Rollout requires Gate GO.
Synthetic delivery plan · Read connections left to right toward dependent activities. 06 / 08

## Slide 7
R1 is most likely; R2 and R5 share the highest impact
Five risks mapped on 1–5 scales. R5 adds a backup-power test before the week-10 gate.
Likelihood ↓ (1 = low; 5 = high)
L / I | 1 | 2 | 3 | 4 | 5
5 |  |  |  |  | 
4 |  |  | R1 |  | 
3 |  |  |  | R3 | R5
2 |  | R4 |  |  | R2
1 |  |  |  |  | 
Impact → (1 = low; 5 = high)
Risk · L / I | Mitigation
R1 · 4 / 3 | Cross-train two crews
R2 · 2 / 5 | Dual-source hardware
R3 · 3 / 4 | Test failover weekly
R4 · 2 / 2 | Audit labels
R5 · 3 / 5 | Test backup power before gate
R5 mitigation directly supports the backup-power gate.
Synthetic risk assessment · Matrix rows show likelihood; columns show impact · L / I = likelihood / impact.
07 / 08

## Slide 8
Approve $440k for Resilient; gate deployment at week 10
Fund the selected option now. At the end of week 10, release rollout only when every threshold passes.
FUNDING REQUEST
$440k
Resilient
Cedar sensor
network
Base case
$155k annual saving
2.8-year payback
$25k three-year net
WEEK 10: GO ONLY IF ALL THREE PASS
1 Uptime ≥99.5%
2 All five sites ≥95% on time
3 Backup-power test passed
ALL PASS → GO
Proceed to the next rollout in weeks 11–14.
ANY FAIL → HOLD
Remediate and re-test; defer rollout until all pass.
Synthetic decision case · 99.8% reference uptime does not replace measured readiness · Validate AND Train remain prerequisites.
08 / 08