## Slide 1
Recommend Balanced Cedar sensor network
Fictional decision committee • Engineering steering group • All data synthetic • Currency $k
$350k
Chosen investment — Balanced
$130k/yr
Annual saving
2.7 years
Simple payback: 350 / 130
$40k
Three-year net saving: 3×130 − 350
DECISION ASKED: Approve Balanced now, conditional on the Week-8 gate.
Balanced delivers 99.0% uptime in 8 weeks — materially above Lean, without Resilient’s $440k spend.
Why now
Six-month actual trails target by 500 readings. Delay keeps the gap open.
Why Balanced
Mid investment, mid saving, 8-week lead. Payback 2.7 years at base saving.
Protection
Week-8 GO only if every threshold passes. Any failure = HOLD. Rollout Weeks 9–12.

## Slide 2
Six-month actual trails target by 500 readings
Readings by month, M1–M6 • All 12 monthly values labelled
Readings per month — Actual vs Target
Chart: 
| M1 | M2 | M3 | M4 | M5 | M6
Actual | 890 | 890 | 940 | 980 | 860 | 900
Target | 970 | 980 | 1070 | 1040 | 930 | 970
5,460
Total actual readings (M1–M6)
5,960
Total target readings (M1–M6)
−500
Gap: actual − target = −500 readings
Every month is below target. The largest monthly shortfalls are M3 (−130) and M2 (−90). This is the performance gap the investment must close.

## Slide 3
Balanced is the middle path on cost and uptime
Reference option prices unchanged • Investment and saving in $k
Option | Investment $k | Saving $k/yr | Uptime % | Lead weeks
Lean | 210 | 95 | 97.5 | 6
Balanced | 350 | 130 | 99.0 | 8
Resilient | 440 | 155 | 99.8 | 10
Selected: Balanced — $350k • $130k/yr • Payback 2.7 years • 3-yr net $40k
Versus Lean (+$140k)
Pays $140k more and takes 2 weeks longer, for +$35k/yr saving and +1.5 points of uptime (99.0% vs 97.5%).
Versus Resilient (−$90k)
Saves $90k upfront and is 2 weeks faster, but forgoes $25k/yr saving and 0.8 points of uptime (99.0% vs 99.8%).
Tradeoff in one line: Balanced buys most of the uptime gain without the top price. It is neither cheapest nor most resilient — the committee is paying for reliability, not for the fastest payback.

## Slide 4
Base case pays back in 2.7 years; downside does not
Balanced investment fixed at $350k • Scenarios at 80% / 100% / 120% of $130k/yr saving
Annual saving by scenario ($k/yr)
Chart: 
| Downside 80% | Base 100% | Upside 120%
Annual saving $k/yr | 104 | 130 | 156
Scenario | Saving $k/yr | Payback yrs | 3-yr net $k
Downside 80% | 104 | 3.4 | −38
Base 100% | 130 | 2.7 | 40
Upside 120% | 156 | 2.2 | 118
Formulas: Payback = 350 / saving. Three-year net = 3 × saving − 350.
Read this honestly: at 80% saving the three-year net is −$38k. Approval relies on validating the base saving before rollout — hence the Week-8 gate.

## Slide 5
Three of five sites are capacity-constrained today
Daily demand and capacity by site — not six-month totals
Site | Demand/day | Capacity/day | On time % | Owner
North | 400 | 360 | 91 | Ari
Central | 400 | 320 | 96 | Bo
South | 260 | 320 | 97 | Cy
East | 290 | 360 | 89 | Dee
West | 350 | 300 | 92 | Eli
1,700/day
Total daily demand (all five sites)
1,660/day
Total daily capacity — shortfall 40/day
Capacity-constrained
(demand > capacity)
• North 400 > 360
• Central 400 > 320
• West 350 > 300
Not constrained: South (260 < 320) and East (290 < 360).
On-time is a separate problem: North 91%, East 89% and West 92% all sit below the 95% gate threshold.

## Slide 6
Build feeds both validation and training before the gate
Two-lane roadmap, Weeks 1–12 • Every activity, week range and dependency shown
Technical
People
Design
Weeks 1–2
Dep: None
Build
Weeks 3–5
Dep: Design
Validate
Weeks 6–8
Dep: Build
Train
Weeks 6–8
Dep: Build
DECISION GATE
Week 8
Dep: Validate AND Train
Rollout
Weeks 9–12
Dep: Gate GO
Critical chain: Design → Build → Validate → Decision Gate (Week 8) → Rollout (Weeks 9–12). Training runs Weeks 6–8 in parallel with validation and must also finish before the gate.

## Slide 7
Two risks need active mitigation before the gate
Likelihood × Impact, each scored 1–5 • Risk IDs plotted at their scored coordinates
Impact →
5
4
3
2
1
1 2 3 4 5
Likelihood → (1 low to 5 high)
R1
R2
R3
R4
ID | Likelihood 1-5 | Impact 1-5 | Mitigation
R1 | 4 | 3 | Cross-train two crews
R2 | 2 | 5 | Dual-source hardware
R3 | 3 | 4 | Test failover weekly
R4 | 2 | 2 | Audit labels
Watch first: R2 (Impact 5) and R3 (3 × 4). R1 is most likely (4) at moderate impact. R4 (2 × 2) is monitor-only.

## Slide 8
Fund $350k now; GO only if every gate threshold passes
Decision gate at Week 8 • Fallback is HOLD — no partial GO
$350k
Funding requested — Balanced
$130k/yr
Base annual saving • Payback 2.7 yrs
Week 8
Decision gate timing
Weeks 9–12
Next rollout if GO
GO requires ALL three thresholds:
1. Uptime ≥ 99.5%
2. All five sites ≥ 95% on time
3. Backup-power test passed
GO
All thresholds pass
→ Rollout
Weeks 9–12
HOLD
Any threshold fails
→ No rollout
Fix, then re-gate
Decision asked today: approve $350k for Balanced and the Week-8 gate rule above. Funding does not authorise rollout — only a full GO at Week 8 does.