## Slide 1
ASTER COLD-CHAIN / OPERATIONS COMMITTEE
Recommend Balanced; make rollout conditional on proof
Invest $350k in regional distribution capacity, with a week-8 gate before rollout in weeks 9–12.
$350k
Investment
$130k
Annual saving
2.7 years
Simple payback
$40k
Three-year net saving
The recommendation carries a readiness gap
Balanced’s reference uptime is 99.0%, below the 99.5% gate. Require measured gate compliance; HOLD rollout if any threshold fails.
All data synthetic • Currency $k • Payback = investment ÷ annual saving • Three-year net = 3 × saving − investment
1 / 8

## Slide 2
Actual shipments missed target in all six months
Six-month throughput • shipments • all 12 monthly values shown
Chart: 
| M1 | M2 | M3 | M4 | M5 | M6
Actual | 870 | 850 | 720 | 910 | 720 | 910
Target | 950 | 970 | 840 | 1040 | 820 | 1050
TOTAL ACTUAL
4,980
TOTAL TARGET
5,670
SHORTFALL
690
shipments
Synthetic data • Shortfall = total target − total actual • Monthly totals are separate from daily site demand and capacity.
2 / 8

## Slide 3
Balanced trades lower cost for an uptime gap
Reference options • prices and performance assumptions remain unchanged
Option | Investment $k | Saving $k/yr | Uptime % | Lead weeks
Lean | 220 | 95 | 97.5 | 6
Balanced | 350 | 130 | 99.0 | 8
Resilient | 440 | 155 | 99.8 | 10
Selected: Balanced
Versus Resilient: $90k less investment, $25k less annual saving and 2 fewer lead weeks.
Tradeoff: reference uptime is below gate
99.0% versus the required ≥99.5%. Selection alone does not establish rollout readiness.
Synthetic data • Currency $k • Lead time is the option reference; rollout remains subject to the week-8 decision gate.
3 / 8

## Slide 4
A 20% savings downside makes three-year net negative
Balanced sensitivity • fixed investment of $350k • annual saving in $k
Chart: 
| Downside 80% | Base 100% | Upside 120%
Annual saving $k | 104 | 130 | 156
Returns at each savings level
Scenario | Payback years | 3-year net $k
Downside | 3.4 | −38
Base | 2.7 | 40
Upside | 2.2 | 118
Downside payback extends beyond three years; base net saving is $40k.
Synthetic data • Payback = 350 ÷ annual saving, rounded to 1 decimal • Three-year net = 3 × annual saving − 350
4 / 8

## Slide 5
South is capacity-constrained despite network headroom
Daily site demand and capacity • current on-time performance and accountable owners
Site | Demand/day | Capacity/day | On time % | Owner
North | 340 | 380 | 95 | Ari
Central | 290 | 330 | 94 | Bo
South | 340 | 320 | 89 | Cy
East | 320 | 340 | 94 | Dee
West | 310 | 340 | 96 | Eli
Demand: 1,600/day
Capacity: 1,710/day
Headroom: 110/day
South has a 20/day deficit. Central, South and East are below the ≥95% on-time gate.
Synthetic data • Capacity-constrained means demand exceeds capacity • Daily figures are separate from six-month shipment totals.
5 / 8

## Slide 6
Validation and training must converge at the week-8 gate
Connected delivery roadmap • dependencies flow left to right • weeks from approval
Technical
People
Design
Weeks 1–2
Build
Weeks 3–5
Validate
Weeks 6–8
Train
Weeks 6–8
Decision gate
Week 8
Rollout
Weeks 9–12
Design starts independently. Build enables Validate and Train; both feed the gate. Only Gate GO enables Rollout.
Synthetic plan • Gate GO requires all thresholds on slide 8 • Any failed threshold means HOLD.
6 / 8

## Slide 7
R1 is most likely; R2 carries the greatest impact
Risk positions use the stated 1–5 scores • pair each risk with its mitigation
Impact ↑ (1–5)
Likelihood → (1–5)
Impact | 1 | 2 | 3 | 4 | 5
5 |  | R2 |  |  | 
4 |  |  | R3 |  | 
3 |  |  |  | R1 | 
2 |  | R4 |  |  | 
1 |  |  |  |  | 
Mitigation for every risk
Risk ID | Mitigation
R1 | Cross-train two crews
R2 | Dual-source hardware
R3 | Test failover weekly
R4 | Audit labels
Synthetic risk assessment • Likelihood increases to the right; impact increases upward • IDs mark the scored coordinates.
7 / 8

## Slide 8
Approve $350k for Balanced; gate the rollout at week 8
Funding decision now: approve the selected investment. Rollout decision later: GO only when every condition passes.
WEEK 8 / ALL THREE CONDITIONS REQUIRED
1 Uptime ≥99.5%
2 All five sites ≥95% on time
3 Backup-power test passed
GO: every threshold passes
Proceed to the next rollout
Weeks 9–12
HOLD: any threshold fails
Hold rollout, remediate and revalidate before a new GO decision.
Readiness gaps today: Balanced uptime 99.0%; Central 94%, South 89% and East 94% on time.
Synthetic decision case • Recommended investment $350k • Annual saving $130k • Payback 2.7 years • Three-year net saving $40k
8 / 8