## Slide 1
Fund Resilient; release rollout after the week 10 gate
Aster cold-chain | Regional distribution capacity | Operations committee
Approve $440k for Resilient: uptime now takes priority over price.
$440k
Chosen investment
$155k
Annual saving
2.8 years
Simple payback
$25k
Three-year net saving
Close the service gap
Six-month shipments miss target by 520. South is short 20 shipments/day.
Prioritize uptime
Resilient lists 99.8% uptime, above the 99.5% gate threshold. Validate it.
Keep release conditional
Week 10: all thresholds must pass. Any failure means HOLD; GO enables weeks 11–14.
All data are synthetic. Currency: $k. Payback = investment / annual saving; three-year net = 3 × saving − investment. 1 / 8

## Slide 2
M4 beats target, but six-month shipments still fall short by 520
M4 actual is 1,080 shipments; the cumulative shortfall is 9.2% of the six-month target.
Monthly shipments | All 12 values shown
Chart: 
| M1 | M2 | M3 | M4 | M5 | M6
Actual | 870 | 850 | 720 | 1080 | 720 | 910
Target | 950 | 970 | 840 | 1040 | 820 | 1050
5,150
Total actual shipments
5,670
Total target shipments
−520
Actual minus target
Period totals are shipments over six months. Daily site demand and capacity are shown separately on slide 5. 2 / 8

## Slide 3
Resilient buys the highest uptime for a $90k premium
Selected option: Resilient. All reference option prices and specifications remain unchanged.
Option | Investment $k | Saving $k/yr | Uptime % | Lead weeks
Lean | 220 | 95 | 97.5 | 6
Balanced | 350 | 130 | 99.0 | 8
Resilient | 440 | 155 | 99.8 | 10
Uptime leads the tradeoff
Versus Balanced: $90k more buys $25k more annual saving and 0.8 percentage points of uptime, with two more lead weeks. Versus Lean: $220k more buys $60k more annual saving.
Listed uptime is not proof
99.8% exceeds the 99.5% threshold by 0.3 points. Demonstrate performance at the week 10 gate.
Reference lead time: Resilient 10 weeks. The release decision is week 10; rollout follows only after Gate GO. 3 / 8

## Slide 4
Resilient’s downside case loses $68k over three years
Investment stays at $440k; annual saving varies to 80%, 100% and 120% of the $155k base.
Annual saving ($k/year)
Chart: 
| Downside 80% | Base 100% | Upside 120%
Annual saving | 124 | 155 | 186
Returns at the same $440k investment
Scenario | Payback years | 3-year net $k
Downside 80% | 3.5 | −68
Base 100% | 2.8 | 25
Upside 120% | 2.4 | 118
Three-year break-even requires $146.7k annual saving—94.6% of base.
Simple payback = 440 / annual saving, rounded to one decimal year. Three-year net = 3 × annual saving − 440. 4 / 8

## Slide 5
South is capacity-constrained despite network headroom
Daily site figures show a local bottleneck; three sites also fall below the 95% on-time gate.
Site | Demand/day | Capacity/day | On time % | Owner
North | 340 | 380 | 95 | Ari
Central | 290 | 330 | 94 | Bo
South | 340 | 320 | 89 | Cy
East | 320 | 340 | 94 | Dee
West | 310 | 340 | 96 | Eli
1,600
Total demand / day
1,710
Total capacity / day
Capacity-constrained: South, short 20/day.
Network headroom: 110/day.
Below 95% on time: Central, South and East.
Demand and capacity are daily shipments; they are distinct from the six-month shipment totals on slide 2. 5 / 8

## Slide 6
Validate and Train feed the week 10 release decision
Activity weeks stay fixed. Both prerequisites finish in week 8; Gate GO enables rollout in weeks 11–14.
Technical
People
Design
Weeks 1–2
No dependency
Build
Weeks 3–5
After Design
Validate
Weeks 6–8
After Build
Train
Weeks 6–8
After Build
Decision gate
Week 10
Validate AND
Train
GO / HOLD
Rollout
Weeks 11–14
After Gate GO
Read connections left to right: prerequisite → dependent activity. Every gate threshold appears on slide 8.
The week 10 gate is a shared decision across Technical and People delivery lanes. 6 / 8

## Slide 7
R5 pairs maximum impact with higher likelihood than R2
Test backup power before the gate; retain all mitigations for R1–R4.
Impact ↑ | 1 low → 5 high
Impact | 1 | 2 | 3 | 4 | 5
5 |  | R2 | R5 |  | 
4 |  |  | R3 |  | 
3 |  |  |  | R1 | 
2 |  | R4 |  |  | 
1 |  |  |  |  | 
Likelihood → | 1 low → 5 high
Mitigations for all five risks
Risk ID | Mitigation
R1 | Cross-train two crews
R2 | Dual-source hardware
R3 | Test failover weekly
R4 | Audit labels
R5 | Test backup power before gate
R5: likelihood 3, impact 5. R2 also has impact 5.
Matrix columns show likelihood; rows show impact. Risk positions use the supplied 1–5 ratings. 7 / 8

## Slide 8
Approve $440k now; require every week 10 threshold for GO
Resilient | $155k annual saving | 2.8-year payback | $25k three-year net saving
Week 10 gate: ALL conditions must pass
Condition | GO threshold
Uptime | At least 99.5%
On-time service | All five sites at least 95% each
Backup power | Backup-power test passed
GO: every condition passes
Authorize the next rollout across all five sites in weeks 11–14.
HOLD: any condition fails
Pause rollout, remediate failed conditions, then repeat the gate before release.
Evidence required: demonstrate uptime, close Central/South/East on-time gaps and pass the backup-power test. Validate AND Train remain gate prerequisites.
All data are synthetic. Funding approval does not replace the week 10 release gate. 8 / 8