## Slide 1
Recommendation: fund Resilient - $440k for $155k/yr saving
Aster cold-chain | Regional distribution capacity | Operations committee decision | All data synthetic | Uptime outranks price
CHOSEN INVESTMENT
$440k
Resilient option
ANNUAL SAVING
$155k/yr
Base case
SIMPLE PAYBACK
2.8 years
440 / 155
THREE-YEAR NET SAVING
$25k
3 x 155 - 440
Why Resilient — uptime outranks price
- 99.8% uptime (highest) and 10-week lead time
- $25k/yr more saving than Balanced, for $90k more investment
- $60k/yr more saving than Lean, +2.3 points uptime
- Protects value with a Week 10 go / no-go gate before rollout
DECISION ASKED TODAY
Approve $440k for Resilient.
Rollout in Weeks 11-14 only if the Week 10 gate returns GO.
Currency: $k | Payback = investment / annual saving | Three-year net = 3 x saving - investment

## Slide 2
Six months fell 520 shipments short: 5,150 actual vs 5,670 target
Shipments by month, M1-M6 - actual vs target (shipments)
Chart: 
| M1 | M2 | M3 | M4 | M5 | M6
Actual | 870 | 850 | 720 | 1080 | 720 | 910
Target | 950 | 970 | 840 | 1040 | 820 | 1050
TOTAL ACTUAL
5,150 shipments
TOTAL TARGET
5,670 shipments
GAP
520 shipments
9.2% below target
Actual was below target in M1-M3 and M5-M6; M4 actual 1,080 beat target 1,040. Gap = 5,670 - 5,150 = 520 shipments.
Aster cold-chain | Six-month performance | Units: shipments

## Slide 3
Resilient wins on uptime: 99.8% is the top score, and uptime outranks price
All option prices shown unchanged. Selected option: Resilient.
Option | Investment $k | Saving $k/yr | Uptime % | Lead weeks
Lean | 220 | 95 | 97.5 | 6
Balanced | 350 | 130 | 99.0 | 8
Resilient | 440 | 155 | 99.8 | 10
Selected-option tradeoff - Resilient ($440k, $155k/yr, 99.8%, 10 weeks)
Vs Lean: pay $220k more and wait 4 weeks longer, gain $60k/yr saving and +2.3 points uptime.
Vs Balanced: pay $90k more and wait 2 weeks longer, gain $25k/yr saving and +0.8 points uptime.
Reference prices remain Lean $220k and Balanced $350k after the Resilient recommendation.

## Slide 4
Downside still pays back in 3.5 years; base case nets $25k over three years
Annual saving by scenario ($k/yr) - Resilient, $440k investment
Chart: 
| Downside 80% | Base 100% | Upside 120%
Annual saving $k/yr | 124 | 155 | 186
Payback and three-year net by scenario
Scenario | Saving $k/yr | Payback yrs | 3-year net $k
Downside 80% | 124 | 3.5 | -68
Base 100% | 155 | 2.8 | 25
Upside 120% | 186 | 2.4 | 118
Downside is -$68k at Year 3: the Week 10 gate must protect against committing rollout on weak evidence.
Scenarios = 80% / 100% / 120% of $155k/yr. Payback = 440 / saving. Three-year net = 3 x saving - 440.
Aster cold-chain | Resilient scenarios | Currency: $k

## Slide 5
South is the only capacity-constrained site: 340/day demand vs 320/day capacity
Daily demand and capacity by site (shipments/day) - not six-month totals
Site | Demand/day | Capacity/day | On time % | Owner
North | 340 | 380 | 95 | Ari
Central | 290 | 330 | 94 | Bo
South | 340 | 320 | 89 | Cy
East | 320 | 340 | 94 | Dee
West | 310 | 340 | 96 | Eli
TOTAL DAILY DEMAND
1,600 / day
TOTAL DAILY CAPACITY
1,710 / day
CONSTRAINED: South only
20/day over capacity; 89% on time
Network headroom is 110/day overall (1,710 - 1,600), but it sits at North, Central, East and West - not South.

## Slide 6
Roadmap: Week 10 Decision gate after Validate + Train, then rollout Weeks 11-14
Technical
People
Design
Weeks 1-2
Dep: None
Build
Weeks 3-5
Dep: Design
Validate
Weeks 6-8
Dep: Build
Train
Weeks 6-8
Dep: Build
DECISION GATE
Week 10
Dep: Validate + Train
Rollout
Weeks 11-14
Dep: Gate GO
Sequence: Design (1-2) -> Build (3-5) -> Validate (6-8) and Train (6-8) -> Decision Gate (Week 10) -> Rollout (11-14, Gate GO only).
Lines show dependencies. Both Validate AND Train must complete before the Week 10 gate. No rollout before a GO decision.

## Slide 7
Top risk is now R5 (L3 x I5): high-impact risks R2, R3 and R5 need mitigation
R1
R2
R3
R4
R5
Likelihood 1-5 (1 at bottom, 5 at top)
Impact 1-5 ->
1 2 3 4 5
5
4
3
2
1
ID | Likelihood 1-5 | Impact 1-5 | Mitigation
R1 | 4 | 3 | Cross-train two crews
R2 | 2 | 5 | Dual-source hardware
R3 | 3 | 4 | Test failover weekly
R4 | 2 | 2 | Audit labels
R5 | 3 | 5 | Test backup power before gate
Read: R1 = L4 x I3, R2 = L2 x I5, R3 = L3 x I4, R4 = L2 x I2, R5 = L3 x I5. Matrix plots Likelihood (vertical) by Impact (horizontal).

## Slide 8
Decision: fund Resilient now; Week 10 gate is GO only if every threshold passes
FUNDING - RESILIENT
Investment: $440k
Annual saving: $155k/yr
Payback: 2.8 years
Three-year net: $25k
GO / NO-GO GATE - WEEK 10
1. Uptime >= 99.5%
2. All five sites >= 95% on time
3. Backup-power test passed
All three must pass (AND).
IF GO
Rollout Weeks 11-14
IF ANY FAILS
HOLD - no rollout
Fallback and next step: HOLD if any threshold fails at Week 10 - fix and re-test before any rollout. On GO, proceed directly to rollout in Weeks 11-14 (Gate dependency: Validate AND Train complete).
Gate rule: Uptime >=99.5% AND all five sites >=95% on time AND backup-power test passed.
Aster cold-chain | Resilient $440k | Currency: $k | All data synthetic