## Slide 1
Fund Balanced; release rollout only after the week 8 gate
Aster cold-chain | Regional distribution capacity | Operations committee
Recommendation: approve the $350k Balanced investment with conditional rollout.
$350k
Chosen investment
$130k
Annual saving
2.7 years
Simple payback
$40k
Three-year net saving
Close the service gap
Six-month actual shipments are 690 below target; South is capacity-constrained.
Resolve the uptime gap
Balanced lists 99.0% uptime; demonstrate at least 99.5% before rollout.
Keep release conditional
Week 8 gate controls GO. Any failed threshold means HOLD.
All data are synthetic. Currency: $k. Payback = investment / annual saving; three-year net = 3 × saving − investment. 1 / 8

## Slide 2
Actual shipments miss the six-month target by 690
Actual is below target in every month; the cumulative shortfall is 12.2% of target.
Monthly shipments | All 12 values shown
Chart: 
| M1 | M2 | M3 | M4 | M5 | M6
Actual | 870 | 850 | 720 | 910 | 720 | 910
Target | 950 | 970 | 840 | 1040 | 820 | 1050
4,980
Total actual shipments
5,670
Total target shipments
−690
Actual minus target
Period totals are shipments over six months. Daily site demand and capacity are shown separately on slide 5. 2 / 8

## Slide 3
Balanced buys a middle-cost path, with an uptime hurdle
Reference option prices and specifications are unchanged. Selected option: Balanced.
Option | Investment $k | Saving $k/yr | Uptime % | Lead weeks
Lean | 220 | 95 | 97.5 | 6
Balanced | 350 | 130 | 99.0 | 8
Resilient | 440 | 155 | 99.8 | 10
Balanced tradeoff
$130k more than Lean buys $35k more annual saving. Versus Resilient, it saves $90k upfront but gives up $25k annual saving and 0.8 points of uptime.
Gate remains binding
99.0% listed uptime is below the 99.5% rollout threshold. Validate performance at week 8.
Lead time is the reference option specification; the delivery roadmap schedules the release decision at week 8. 3 / 8

## Slide 4
The downside case produces a $38k three-year net loss
Balanced investment stays at $350k; annual saving varies to 80%, 100% and 120% of base.
Annual saving ($k/year)
Chart: 
| Downside 80% | Base 100% | Upside 120%
Annual saving | 104 | 130 | 156
Return at the same $350k investment
Scenario | Payback years | 3-year net $k
Downside 80% | 3.4 | −38
Base 100% | 2.7 | 40
Upside 120% | 2.2 | 118
Three-year break-even requires $116.7k annual saving.
Simple payback = 350 / annual saving, rounded to one decimal year. Three-year net = 3 × annual saving − 350. 4 / 8

## Slide 5
South is capacity-constrained despite network headroom
Daily site figures show a local bottleneck; three sites also fall below the 95% on-time gate.
Site | Demand/day | Capacity/day | On time % | Owner
North | 340 | 380 | 95 | Ari
Central | 290 | 330 | 94 | Bo
South | 340 | 320 | 89 | Cy
East | 320 | 340 | 94 | Dee
West | 310 | 340 | 96 | Eli
1,600
Total demand / day
1,710
Total capacity / day
Capacity-constrained: South, short 20/day.
Network headroom: 110/day.
Below 95% on time: Central, South and East.
Demand and capacity are daily shipments; they are distinct from the six-month shipment totals on slide 2. 5 / 8

## Slide 6
Validation and training converge at the week 8 decision
Both lanes must finish before the gate; rollout in weeks 9–12 depends on Gate GO.
Technical
People
Design
Weeks 1–2
No dependency
Build
Weeks 3–5
After Design
Validate
Weeks 6–8
After Build
Train
Weeks 6–8
After Build
Decision gate
Week 8
Validate AND Train
GO / HOLD
Rollout
Weeks 9–12
After Gate GO
Connectors show prerequisite → dependent activity, read from left to right. Gate criteria appear on slide 8.
The gate is a shared decision across Technical and People delivery lanes. 6 / 8

## Slide 7
Prioritize R1 and R3; protect against R2’s maximum impact
1
2
3
4
5
1
2
3
4
5
R1
R2
R3
R4
Impact ↑ (1 low → 5 high)
Likelihood → (1 low → 5 high)
Risk ID | Mitigation
R1 | Cross-train two crews
R2 | Dual-source hardware
R3 | Test failover weekly
R4 | Audit labels
R1: likelihood 4, impact 3 | R3: 3, 4
R2: likelihood 2, impact 5 | R4: 2, 2
Risk positions use the supplied 1–5 ratings. 7 / 8

## Slide 8
Approve $350k now; require every week 8 threshold for GO
Funding request: Balanced | $130k annual saving | 2.7-year payback | $40k three-year net saving
Week 8 decision gate: ALL conditions must pass
Condition | GO threshold
Uptime | At least 99.5%
On-time service | All five sites at least 95% each
Backup power | Backup-power test passed
GO: every condition passes
Authorize the next rollout across the five sites in weeks 9–12.
HOLD: any condition fails
Pause rollout, remediate failed conditions, then repeat the gate before release.
Evidence to close: Balanced lists 99.0% uptime; Central, South and East currently miss 95% on time.
All data are synthetic. Funding approval does not replace the week 8 release gate. 8 / 8